## 2026
S. No | PGr | CC | End User | Dept. | PR # | Material Code | PR date | RFQ Date | Short Description | Stage | Current Status | PO Number | Vendor Name | PO Date | PO DOD | Issue to Vendor | Ackn | TOP | CUR | PO Value | Disc. in SAR | Incoterm | Delivery Point | Delivery Status | Actual DOD
1 |  | CC970 | User 31 | Mechanical | PR450870 | MAT60390 | 2025/11/26 | 2025/11/30 | CENTRIFUGAL PUMP MECHANICAL SEAL | RFQ |  | 4514149339 | Al Mojil Group | 2025/12/22 |  | 2025/12/22 | No | 60 | EUR | 184602.19 | 13543.57 |  |  | Pending
2 | HEY | CC786 | User 45 | Process | PR874120 | MAT41138 | 20-Dec-2025 |  | UPS BATTERY REPLACEMENT 110V | On Hold |  |  | SKF Arabia |  |  |  | Yes |  | SAR |  |  | FOB | Site
3 | FAV | CC886 | User 26 | Mechanical | PR323259 | MAT91196 | 08-Mar-2026 | 11-Mar-2026 | SAFETY VALVE TESTING AND CALIBRATION | On Hold | In Progress |  | Al Mojil Group |  |  |  | Yes | 30 | SAR |  |  | DAP | Port
4 | HEY | CC712 | User 29 | Process | PR714347 | MAT12562 | 2026-07-26 |  | PROCESS ISOLATION WINDOW SIGHT GLASS | PR | [7 empty] | 90 |  |  |  |  | Warehouse | N/A
5 | HEV | CC186 | User 41 | Mechanical | PR313872 | MAT91370 | 2026-04-08 | 2026-04-21 | PAINTING AND INSULATION CLADDING | On Hold |  |  | SABIC INDUSTRIAL |  |  |  | Yes | 90 | SAR |  |  | CIF | Port
6 | FAV | CC550 | User 39 | Process | PR788677 | MAT74629 | 12/31/2025 | 01/09/2026 | COMPRESSOR OIL AND FILTER KIT | Cancelled | In Progress | 4514131509 | GE Power Arabia | 01/25/2026 | 04/21/2026 | 01/25/2026 | YES | 45 | SAR | 93204.94 | 2722.66 | DAP |  | Delivered | 04/14/2026
7 | HEY | CC558 | User 25 | Instrumentation | PR973167 | MAT83691 | 06-May-2026 | 09-May-2026 | PLC SPARE PARTS AND MODULES | PR | In Progress | 4514150035 | SABIC Industrial | 12-May-2026 | 31-Aug-2026 | 12-May-2026 |  | 60 | EUR | 76652.26 | 2416.4 | CIF | Port
8 | HEV | CC291 | User 42 | Instrumentation | PR907575 | MAT59475 | 25/12/2025 | 29/12/2025 | SAFETY VALVE TESTING AND CALIBRATION | On Hold | OPEN | 4514123932 | Emerson Process | 04/01/2026 | 08/04/2026 |  |  | 45 |  | 15581.69 | 1006.85 | CIF | Warehouse | In Transit
9 | HEY | CC737 | User 37 | Electrical | PR334715 | MAT43342 | 04/09/2026 |  | UPS BATTERY REPLACEMENT 110V | PO |  |  | UNKNOWN VENDOR |  |  |  | YES | 60 | SAR |  |  | CIF | Warehouse
10 | HEV | CC121 | User 14 | Instrumentation | PR542932 | MAT42409 | 2026/04/10 | 2026/04/13 | SAFETY VALVE TESTING AND CALIBRATION | PO | Closed |  | Saudi Aramco Supply |  |  |  |  | 45 |  |  |  | CIF |  | N/A
11 | HEY | CC434 | User 42 | Instrumentation | PR973053 | MAT26389 | 2026/03/11 |  | CENTRIFUGAL PUMP MECHANICAL SEAL | Delivered | OPEN | [6 empty] | 30 |  |  |  | FOB
12 | HEY | CC392 | User 31 | Utilities | PR379390 | MAT20587 | 2026-07-05 |  | LABORATORY CHEMICALS AND REAGENTS | On Hold | In Progress |  | SABIC INDUSTRIAL |  |  |  | Yes | 45 | EUR |  |  | DAP |  | Pending
13 | HEY | CC615 | User 15 | Utilities | PR867292 | MAT46406 | 2026/05/17 | 2026/06/01 | UPS BATTERY REPLACEMENT 110V | On Hold | Closed | 4514123336 | UNKNOWN VENDOR | 2026/06/11 | 2026/09/21 | 2026/06/11 | Yes | 30 | EUR | 34454.6 | 851.55 | DAP | Port | pending
14 | FAV | CC698 | User 33 | Process | PR850638 | MAT38441 | 17-Apr-2026 |  | PAINTING AND INSULATION CLADDING | PO |  |  | Saudi aramco supply |  |  |  | No | 90 | USD |  |  | DAP | Warehouse | Pending
15 | HEY | CC162 | User 47 | Civil | PR700989 | MAT30076 | 2025-11-27 | 2025-12-09 | HEAT EXCHANGER CLEANING SERVICE | Cancelled | In Progress | 4514112239 | Al-Rushaid Trading Co. | 2025-12-28 | 2026-02-03 |  |  | 30 | EUR |  |  | DAP | Site | Done | 2026-02-06
16 | HEV | CC729 | User 10 | Process | PR622884 | MAT15610 | 09-Jul-2026 | 26-Jul-2026 | SAFETY VALVE TESTING AND CALIBRATION |  | Closed | 4514199573 | Yokogawa ME | 13-Aug-2026 | 14-Oct-2026 | 13-Aug-2026 | Yes | 45 | USD | 157237.15 | 11755.02 | CIF | Port | In Transit
17 | HEY | CC129 | User 12 | Electrical | PR538701 | MAT85000 | 10/04/2026 | 21/04/2026 | SCAFFOLDING ERECTION AND DISMANTLING | On Hold | OPEN | 4514132022 | Emerson Process | 08/05/2026 |  | 08/05/2026 | Yes | 30 |  | 167412.54 | 12077.15 | CIF | Warehouse
18 | HEY | CC236 | User 49 | MECH | PR758711 | MAT29884 | 27/06/2026 | 29/06/2026 | FLOWMETER CALIBRATION AND CERTIFICATION | PR | OPEN | 4514180977 | GE Power Arabia | 03/07/2026 | 25/07/2026 | 03/07/2026 | YES |  |  |  |  | FOB |  | pending
19 | HEV | CC479 | User 13 | Instrumentation | PR367942 | MAT92239 | 09-Aug-2026 |  | PLC SPARE PARTS AND MODULES |  | Open |  | SKF Arabia |  |  |  |  | 60 | SAR
20 | FAV | CC458 | User 28 | MECH | PR701431 | MAT16890 | 04/20/2026 | 05/08/2026 | ANNUAL PM SERVICE FOR CHILLER UNIT | PR | OPEN | 4514116971 | Saudi aramco supply | 05/21/2026 | 09/18/2026 | 05/21/2026 | No | 45 |  | 99906.36 | 7888.84 | DAP |  | pending
21 | FAV | CC363 | User 47 | Civil | PR173365 | MAT50753 | 2026/07/15 | 2026/07/31 | LEVEL TRANSMITTER INSTALLATION | Delivered | In Progress |  | Al-Rushaid Trading Co. |  |  |  | YES | 90 | EUR |  |  | DAP | Warehouse
22 | HEY | CC228 | User 9 | INST | PR240832 | MAT31647 | 2026-02-15 | 2026-03-06 | HAWKER WET CELL BATTERY SET 24V | PO | OPEN | 4514137176 | Al-Rushaid Trading Co. | 2026-03-19 |  | 2026-03-19 | No | 30 | SAR | 105367.89 | 4598.03 |  | Site | Pending
23 | HEY | CC104 | User 20 | Mechanical | PR657759 | MAT71267 | 17-Jul-2026 | 31-Jul-2026 | SCAFFOLDING ERECTION AND DISMANTLING | RFQ |  |  | SABIC INDUSTRIAL | [5 empty] | EUR |  |  |  | Warehouse | Pending
24 | HEV | CC168 | User 15 | Electrical | PR397695 | MAT18034 | 07/17/2026 | 07/24/2026 | LEVEL TRANSMITTER INSTALLATION | RFQ | Closed | 4514169540 | Al Mojil Group | 08/10/2026 |  | 08/10/2026 | YES | 90 | EUR | 34108.1 | 1541.9
25 |  | CC922 | User 34 | Civil | PR806934 | MAT14524 | 2026-03-31 |  | FIRE DETECTION SYSTEM MAINTENANCE | PO | OPEN |  | UNKNOWN VENDOR |  |  |  | Yes | 45 | SAR |  |  | DAP | Warehouse
26 | FAV | CC122 | User 1 | Civil | PR408700 | MAT17224 | 03/13/2026 |  | PRESSURE TRANSMITTER HART PROTOCOL |  | In Progress |  | Schneider Electric KSA |  |  |  | No | 90 | EUR |  |  |  | Site | Pending
27 | FAV | CC100 | User 13 | INST | PR127881 | MAT91640 | 11/03/2025 | 11/15/2025 | COMPRESSOR OIL AND FILTER KIT | Delivered | OPEN | 4514165152 | Endress+Hauser | 12/03/2025 | 01/26/2026 | 12/03/2025 |  | 60 | EUR |  |  | DAP |  | In Transit
28 |  | CC966 | User 9 | Civil | PR565519 | MAT82354 | 2026/04/28 |  | GATE VALVE 6 INCH CLASS 300 | Delivered | OPEN |  | UNKNOWN VENDOR |  |  |  | No | 60 | USD |  |  | CIF | Warehouse
29 | HEY | CC648 | User 1 | Utilities | PR421447 | MAT22771 | 06/06/2026 |  | PAINTING AND INSULATION CLADDING | On Hold |  |  | Yokogawa ME |  |  |  |  | 60 | SAR
30 | HEY | CC350 | User 7 |  | PR894481 | MAT21121 | 2026/05/12 | 2026/05/19 | LABORATORY CHEMICALS AND REAGENTS | PO | Closed | 4514166795 |  | 2026/06/06 | 2026/06/22 |  |  | 90 | USD | 168839.31 | 6794.44 |  | Port | Delivered | 2026/06/19
31 |  | CC640 | User 5 | Electrical | PR660343 | MAT38090 | 26/06/2026 |  | HEAT EXCHANGER CLEANING SERVICE | Cancelled | Open |  | Yokogawa ME |  |  |  |  | 45 | USD |  |  | CIF | Warehouse
32 | HEY | CC891 | User 35 | Utilities | PR572500 | MAT59356 | 28-May-2026 | 02-Jun-2026 | LABORATORY CHEMICALS AND REAGENTS | Delivered | Closed | 4514180145 | GE Power Arabia | 15-Jun-2026 | 20-Jul-2026 | 15-Jun-2026 |  | 90 | USD | 174389.76 | 4672.5 |  | Port | Pending
33 | HEY | CC191 | User 33 | MECH | PR875806 | MAT38115 | 11/22/2025 |  | CENTRIFUGAL PUMP MECHANICAL SEAL | Delivered | OPEN |  | Al-Rushaid Trading Co. |  |  |  | No | 60 |  |  |  | CIF | Port | N/A
34 | HEY | CC789 | User 14 | Electrical | PR823254 | MAT77225 | 04/27/2026 |  | HAWKER WET CELL BATTERY SET 24V |  |  |  | Siemens Arabia |  |  |  | YES | 45 | SAR |  |  |  |  | Pending
35 | HEY | CC280 | User 11 | Mechanical | PR346001 | MAT36418 | 2026-02-09 | 2026-02-23 | COOLING TOWER FILL MEDIA REPLACEMENT |  | Closed | 4514124879 |  | 2026-03-22 | 2026-05-01 | 2026-03-22 |  |  | EUR | 74711.83 | 3329.52 |  | Port | In Transit
36 | HEV | CC556 | User 35 | INST | PR187065 | MAT18386 | 20-Jan-2026 | 29-Jan-2026 | HAWKER WET CELL BATTERY SET 24V |  | Open |  | SKF Arabia |  |  |  | No | 90 | SAR |  |  | FOB | Site
37 |  | CC375 | User 20 |  | PR503517 | MAT67543 | 29-Jun-2026 |  | PLC SPARE PARTS AND MODULES | Cancelled | Open |  | Al-Rushaid Trading Co. |  |  |  |  | 90 | SAR |  |  | FOB | Site
38 | HEY | CC725 | User 1 | Civil | PR470701 | MAT40051 | 29/07/2026 | 12/08/2026 | CENTRIFUGAL PUMP MECHANICAL SEAL | PR |  | 4514152750 | Yokogawa ME | 17/08/2026 | 09/11/2026 | 17/08/2026 | YES | 60 | SAR |  |  | FOB | Site | In Transit
39 | FAV | CC145 | User 1 | Mechanical | PR531696 | MAT42511 |  | 2026/01/12 | SAFETY VALVE TESTING AND CALIBRATION |  | OPEN | 4514146001 | SABIC INDUSTRIAL | 2026/02/07 | 2026/05/25 | 2026/02/07 | Yes | 30 | SAR | 246206.72 | 13705.52
40 | HEY | CC140 | User 43 | Utilities | PR794404 | MAT14763 | 31-Dec-2025 |  | PLC SPARE PARTS AND MODULES |  | Open |  | GE Power Arabia | [5 empty] | SAR |  |  | FOB | Site
41 | FAV | CC720 | User 50 | Instrumentation | PR352797 | MAT73871 | 2026-05-27 | 2026-05-30 | PRESSURE TRANSMITTER HART PROTOCOL | PR |  |  | Al-Rushaid Trading Co. |  |  |  | No |  | EUR |  |  |  | Site | Pending
42 | HEY | CC723 | User 34 | Electrical | PR562063 | MAT23907 | 2025-12-27 | 2026-01-09 | COOLING TOWER FILL MEDIA REPLACEMENT | RFQ | Closed | 4514192035 |  | 2026-01-26 | 2026-04-29 | 2026-01-26 | Yes | 60 | USD |  |  |  | Site | Del | 2026-04-24
43 | FAV | CC686 | User 50 | Utilities | PR597948 | MAT30486 | 2025-11-14 |  | SCAFFOLDING ERECTION AND DISMANTLING | Delivered | OPEN |  | SKF Arabia |  |  |  | No | 30 | SAR |  |  | CIF | Port | N/A
44 | HEY | CC855 | User 43 | Civil | PR679759 | MAT94397 | 2025-11-11 | 2025-11-21 | UPS BATTERY REPLACEMENT 110V |  | Closed | 4514141533 | Al-Rushaid Trading Co. | 2025-12-17 | 2026-01-15 | 2025-12-17 | No | 45 |  |  |  | CIF | Site | DELIVERED | 2026-01-22
45 | FAV | CC708 | User 27 | Utilities | PR374098 | MAT66812 | 15-Nov-2025 | 30-Nov-2025 | GATE VALVE 6 INCH CLASS 300 | PO | Open | 4514188875 | Emerson Process | 24-Dec-2025 | 21-Apr-2026 |  |  | 60 | EUR | 121270.86 | 5070.58 | DAP | Port | pending
46 | HEY | CC846 | User 31 | MECH | PR312594 | MAT40157 | 08/11/2025 |  | SCAFFOLDING ERECTION AND DISMANTLING | On Hold | OPEN |  | SABIC Industrial | [8 empty] | DAP | Warehouse
47 | HEV | CC294 | User 35 | MECH | PR358045 | MAT60391 | 20-Mar-2026 | 06-Apr-2026 | LEVEL TRANSMITTER INSTALLATION | Cancelled | In Progress | 4514137538 |  | 23-Apr-2026 |  |  |  | 60 | USD | 38651.99 | 2719.47 | DAP | Port
48 | FAV | CC969 | User 31 | MECH | PR354167 | MAT88808 | 2026-07-25 |  | ELECTRICAL CABLE 3CX16MM ARMOURED | PR | Closed |  | Saudi aramco supply |  |  |  | YES | 90 | SAR |  |  | FOB | Site | N/A
49 | HEV | CC454 | User 4 | Process | PR339800 | MAT81620 | 2026-04-27 | 2026-05-17 | SCAFFOLDING ERECTION AND DISMANTLING | PR | OPEN | 4514110518 | SABIC INDUSTRIAL | 2026-05-30 | 2026-09-14 | 2026-05-30 | No | 90 | USD | 214652.69 | 14183.2 |  | Site | In Transit
50 |  | CC475 | User 33 | Mechanical | PR909307 | MAT32206 | 2026/01/11 |  | CENTRIFUGAL PUMP MECHANICAL SEAL | Delivered |  |  | Emerson Process |  |  |  | YES |  | SAR |  |  | FOB | Warehouse | Pending
51 | HEY | CC995 | User 23 | Mechanical | PR932721 | MAT57859 | 05/11/2026 | 05/14/2026 | COMPRESSOR OIL AND FILTER KIT | Delivered | Open | 4514168969 | Yokogawa ME | 05/31/2026 | 08/07/2026 | 05/31/2026 | No | 30 | USD | 21720.19 | 614.99 | CIF | Site | Done | 07/30/2026
52 | HEV | CC320 | User 7 | Utilities | PR751425 | MAT83614 | 11/15/2025 | 11/24/2025 | SAFETY VALVE TESTING AND CALIBRATION | Delivered | Closed | 4514155788 | ABB Saudi Arabia | 12/13/2025 | 04/10/2026 | 12/13/2025 | No | 30 | USD | 160198.48 | 9260.89 | CIF | Site | Delivered | 04/05/2026
53 | HEY | CC954 | User 29 |  | PR161238 | MAT73865 | 2026/06/26 |  | HEAT EXCHANGER CLEANING SERVICE |  | Open |  | Al-Rushaid Trading Co. |  |  |  | Yes |  |  |  |  | DAP | Port | N/A
54 | HEY | CC185 | User 49 | INST | PR732267 | MAT81270 | 2026-07-03 | 2026-07-16 | FIRE DETECTION SYSTEM MAINTENANCE | PR |  | 4514131707 | Honeywell KSA | 2026-08-07 | 2026-11-05 | 2026-08-07 |  | 90 |  | 242292.41 | 6702.3 | DAP | Port
55 | FAV | CC910 | User 4 | Mechanical | PR915786 | MAT24711 | 2026-04-09 |  | COMPRESSOR OIL AND FILTER KIT | On Hold | Open |  | Honeywell KSA |  |  |  | YES |  | EUR |  |  | DAP | Port | N/A
56 |  | CC782 | User 35 | Mechanical | PR638225 | MAT30801 | 2026-02-17 | 2026-03-03 | HAWKER WET CELL BATTERY SET 24V | Cancelled |  | 4514163387 | SABIC INDUSTRIAL | 2026-03-22 | 2026-06-28 |  |  | 90 |  | 95774.59 | 3391.43 | CIF
57 | HEV | CC618 | User 42 | Process | PR840455 | MAT22986 | 2026/05/16 | 2026/05/30 | SAFETY VALVE TESTING AND CALIBRATION | PR | Open | 4514125089 | GE Power Arabia | 2026/06/22 | 2026/08/31 | 2026/06/22 |  | 45 | SAR | 40148.45 | 3035.57 |  | Site | pending
58 |  | CC621 | User 28 | Electrical | PR217770 | MAT55416 | 01/26/2026 | 02/03/2026 | SAFETY VALVE TESTING AND CALIBRATION | On Hold | Open | 4514154864 | ABB Saudi Arabia | 02/23/2026 | 05/27/2026 |  | Yes | 45 |  | 221764.35 | 16891.31 | DAP |  | Partial Delivery
59 | HEY | CC691 | User 22 | Civil | PR797864 | MAT36404 | 14/05/2026 | 28/05/2026 | CENTRIFUGAL PUMP MECHANICAL SEAL | PO | Open |  | GE Power Arabia |  |  |  | No | 90 | USD |  |  | DAP
60 | HEV | CC130 | User 4 | MECH | PR772351 | MAT96348 | 03/24/2026 |  | SCAFFOLDING ERECTION AND DISMANTLING | On Hold |  |  | Al-Rushaid Trading Co. |  |  |  |  | 45 | USD |  |  |  | Warehouse | Pending
61 | HEY | CC321 | User 15 | Electrical | PR391144 | MAT47971 | 04/25/2026 |  | SAFETY VALVE TESTING AND CALIBRATION | On Hold | OPEN |  | SABIC INDUSTRIAL |  |  |  | Yes | 60 | EUR |  |  | CIF | Site | Pending
62 | HEY | CC349 | User 50 | Utilities | PR342846 | MAT67496 | 14-Dec-2025 |  | PAINTING AND INSULATION CLADDING | PO | In Progress |  | Al-Rushaid Trading Co. |  |  |  |  | 90 | USD |  |  | FOB | Port
63 | HEY | CC787 | User 12 | Process | PR526775 | MAT37487 | 2026-07-03 | 2026-07-14 | PLC SPARE PARTS AND MODULES | RFQ | Closed | 4514185066 | Saudi Aramco Supply | 2026-08-09 |  |  | YES | 90 |  | 64008.61 | 2171.07
64 |  | CC751 | User 26 | Electrical | PR181764 | MAT66905 | 2025/12/29 | 2026/01/18 | ELECTRICAL CABLE 3CX16MM ARMOURED | Cancelled | OPEN | 4514110467 |  | 2026/02/06 | 2026/05/27 | 2026/02/06 |  | 60 | SAR |  |  | DAP | Port | Partial Delivery
65 | HEY | CC155 | User 12 | Civil | PR400120 | MAT14197 | 04/15/2026 | 04/28/2026 | COOLING TOWER FILL MEDIA REPLACEMENT | PO |  | 4514118306 | SKF Arabia | 05/13/2026 | 06/16/2026 | 05/13/2026 | Yes | 30 | USD | 40292.98 | 2892.16 | FOB | Warehouse | Done | 06/23/2026
66 | FAV | CC618 | User 38 | INST | PR979586 | MAT59415 | 2026/04/22 | 2026/05/10 | HEAT EXCHANGER CLEANING SERVICE | Delivered |  | 4514134604 | Al-Rushaid Trading Co. | 2026/05/20 | 2026/08/02 | 2026/05/20 |  | 45 |  | 239449.52 | 18427.54 | DAP | Warehouse | Delivered | 2026/08/10
67 | FAV | CC387 | User 15 | MECH | PR949304 | MAT31165 | 2026/07/06 | 2026/07/20 | FLOWMETER CALIBRATION AND CERTIFICATION | RFQ | OPEN | 4514171609 | Al-Rushaid Trading Co. | 2026/08/02 | 2026/11/05 |  | Yes | 45 | SAR | 52107.59 | 4063.07 |  | Site | In Transit
68 |  | CC601 | User 34 | Mechanical | PR484092 | MAT64640 | 2025/11/04 | 2025/11/18 | COOLING TOWER FILL MEDIA REPLACEMENT | On Hold | In Progress | 4514175363 | Schneider Electric KSA | 2025/11/27 | 2026/03/18 | 2025/11/27 | YES | 60 | USD | 164420.13 | 7720.3 | DAP | Site | Partial Delivery
69 | HEY | CC433 | User 37 | MECH | PR165753 | MAT76601 | 2025-12-19 | 2025-12-27 | GATE VALVE 6 INCH CLASS 300 | On Hold | Open | 4514144740 | ABB Saudi Arabia | 2026-01-09 | 2026-03-11 | 2026-01-09 |  | 60 |  | 85568.89 | 4909.64 | FOB | Port | Done | 2026-03-19
70 | HEY | CC556 | User 32 | Process | PR773311 | MAT16473 | 10-Jan-2026 | 21-Jan-2026 | ELECTRICAL CABLE 3CX16MM ARMOURED | Delivered | Open | 4514126667 | SABIC Industrial | 17-Feb-2026 | 07-May-2026 | 17-Feb-2026 | No | 30 | EUR | 109807.74 | 2600.74 | FOB | Warehouse | Partial Delivery
71 | HEY | CC351 | User 32 | Electrical | PR668171 | MAT79475 | 04/19/2026 | 04/22/2026 | PROCESS ISOLATION WINDOW SIGHT GLASS | RFQ |  | 4514147600 | Emerson Process | 05/04/2026 | 08/27/2026 |  |  | 60 | SAR |  |  |  | Site | Partial Delivery
72 | FAV | CC225 | User 21 | INST | PR921055 | MAT66178 | 2025-11-18 | 2025-11-30 | LEVEL TRANSMITTER INSTALLATION | PR | Open | 4514196351 | ABB Saudi Arabia | 2025-12-15 | 2026-03-31 |  |  | 90 | SAR | 133701.7 | 3150.65 | DAP |  | Delivered | 2026-03-26
73 |  | CC490 | User 16 |  | PR674359 | MAT27609 | 2026-05-14 | 2026-05-17 | LEVEL TRANSMITTER INSTALLATION | On Hold | Closed |  | Schneider Electric KSA |  |  |  |  | 30
74 | HEY | CC613 | User 8 | Process | PR875854 | MAT85948 | 05/04/2026 | 05/20/2026 | PLC SPARE PARTS AND MODULES | PO | Closed | 4514136295 | Yokogawa ME | 05/26/2026 | 07/10/2026 | 05/26/2026 |  | 60 | USD | 196789.14 | 14599.9 | CIF | Site | Done | 07/17/2026
75 | HEY | CC963 | User 41 | Utilities | PR206162 | MAT96512 | 2025-12-12 |  | SAFETY VALVE TESTING AND CALIBRATION | PO | Open |  | Parker Hannifin | [8 empty] | FOB | Site | Pending
76 | FAV | CC569 | User 19 | Mechanical | PR118878 | MAT75666 | 12/09/2025 | 12/11/2025 | COMPRESSOR OIL AND FILTER KIT | Cancelled | Closed | 4514190354 | Saudi Aramco Supply | 12/28/2025 |  | 12/28/2025 |  |  |  | 192449.83 | 6252.36 | CIF | Site | Pending
77 | HEY | CC928 | User 35 | Mechanical | PR668359 | MAT67075 | 2026-04-26 | 2026-05-15 | HAWKER WET CELL BATTERY SET 24V | On Hold | In Progress | 4514155428 | Al Mojil Group | 2026-05-31 | 2026-08-18 | 2026-05-31 |  | 60 |  | 134708.99 | 10767.92 |  |  | DELIVERED | 2026-08-18
78 | FAV | CC902 | User 35 | INST | PR674952 | MAT80312 | 2026/03/15 | 2026/03/17 | HEAT EXCHANGER CLEANING SERVICE | RFQ | Closed | 4514115001 | SABIC INDUSTRIAL | 2026/03/27 |  |  |  | 90 | USD | 102558.35 | 7068.86 |  | Site | Pending
79 | HEY | CC602 | User 14 | Electrical | PR527664 | MAT28951 | 2026-05-15 | 2026-05-28 | GATE VALVE 6 INCH CLASS 300 | Cancelled | Closed | 4514126183 | Al-Rushaid Trading Co. | 2026-06-25 | 2026-08-17 | 2026-06-25 |  | 60 |  | 229681.11 | 7203.32 | DAP | Warehouse | DELIVERED | 2026-08-15
80 | HEY | CC322 | User 2 | Mechanical | PR284280 | MAT20502 | 2025-11-23 |  | ANNUAL PM SERVICE FOR CHILLER UNIT | PR | Open |  | Siemens Arabia |  |  |  |  | 90 | EUR |  |  | DAP | Warehouse
81 | FAV | CC632 | User 47 | Instrumentation | PR142630 | MAT65365 | 2026-04-19 | 2026-05-08 | PRESSURE TRANSMITTER HART PROTOCOL | PO | OPEN | 4514192920 | GE Power Arabia | 2026-05-28 |  |  | YES | 30 |  | 153632.57 | 3736.21 | CIF | Warehouse | N/A
82 | FAV | CC156 | User 6 | Process | PR975207 | MAT85364 | 12/18/2025 | 12/20/2025 | FIRE DETECTION SYSTEM MAINTENANCE | PR |  |  | Siemens Arabia |  |  |  | YES |  | SAR |  |  |  | Warehouse | N/A
83 | HEY | CC284 | User 39 | MECH | PR830904 | MAT42944 | 06-Feb-2026 | 11-Feb-2026 | HEAT EXCHANGER CLEANING SERVICE | Cancelled |  | 4514116731 |  | 02-Mar-2026 | 22-May-2026 | 02-Mar-2026 |  |  | SAR | 177630.61 | 10159.25 | DAP | Site | pending
84 | HEY | CC586 | User 30 | MECH | PR135788 | MAT86074 | 2026/07/18 |  | ANNUAL PM SERVICE FOR CHILLER UNIT | On Hold | OPEN |  | Honeywell KSA |  |  |  |  | 45 | SAR |  |  |  | Site
85 | HEV | CC746 | User 42 | MECH | PR637682 | MAT96025 | 2026-02-22 | 2026-03-10 | SCAFFOLDING ERECTION AND DISMANTLING | On Hold |  | 4514161484 | UNKNOWN VENDOR | 2026-04-09 | 2026-05-03 | 2026-04-09 |  | 45 |  | 133277.64 | 3979.62 | FOB | Site | Partial Delivery
86 | HEY | CC586 | User 5 | Electrical | PR875968 | MAT84553 | 17-May-2026 |  | LEVEL TRANSMITTER INSTALLATION | PR | In Progress |  | GE Power Arabia |  |  |  |  | 60 | EUR |  |  |  | Port | N/A
87 | HEY | CC902 | User 35 | Utilities | PR243274 | MAT72476 | 2026-03-27 | 2026-04-15 | LEVEL TRANSMITTER INSTALLATION | Cancelled |  | 4514197369 | Al Mojil Group | 2026-05-04 | 2026-07-08 | 2026-05-04 |  | 30 |  | 86811.39 | 3219.15 | DAP |  | pending
88 | HEY | CC336 | User 23 | Process | PR822111 | MAT94689 | 2026/01/24 | 2026/01/27 | LEVEL TRANSMITTER INSTALLATION | RFQ | In Progress |  | Endress+Hauser |  |  |  | Yes | 30 |  |  |  |  | Site | N/A
89 | HEY | CC862 | User 50 | MECH | PR960094 | MAT79904 | 07/16/2026 | 07/19/2026 | LABORATORY CHEMICALS AND REAGENTS | PO | In Progress | 4514112794 | UNKNOWN VENDOR | 08/02/2026 | 10/16/2026 | 08/02/2026 | Yes | 60 | EUR | 153814.1 | 9186.7 | DAP | Site | In Transit
90 |  | CC444 | User 38 | INST | PR643106 | MAT40276 | 01/01/2026 |  | CONTROL VALVE ACTUATOR REPAIR |  | Open |  | Al-Rushaid Trading Co. |  |  |  |  | 45 | SAR |  |  | DAP | Site
91 | HEY | CC841 | User 18 | Civil | PR626963 | MAT81779 | 04-May-2026 |  | PROCESS ISOLATION WINDOW SIGHT GLASS | Delivered | OPEN |  | ABB Saudi Arabia |  |  |  |  | 60 |  |  |  | DAP | Site | Pending
92 | HEV | CC519 | User 4 | Mechanical | PR518130 | MAT26686 | 03/08/2026 | 03/26/2026 | PLC SPARE PARTS AND MODULES | RFQ | Closed | 4514165834 | Al-Rushaid Trading Co. | 04/11/2026 | 06/27/2026 | 04/11/2026 |  | 30 | SAR |  |  | DAP | Port | Pending
93 | HEV | CC460 | User 22 | INST | PR148187 | MAT74626 | 2026-01-30 | 2026-02-05 | COOLING TOWER FILL MEDIA REPLACEMENT | Delivered | Closed | 4514174239 | UNKNOWN VENDOR | 2026-03-05 | 2026-04-22 | 2026-03-05 | Yes | 90 |  | 3980.26 | 226.9
94 |  | CC528 | User 11 |  | PR460463 | MAT68549 | 2026/02/25 | 2026/03/14 | COOLING TOWER FILL MEDIA REPLACEMENT | RFQ | Open | 4514124186 | Schneider Electric KSA | 2026/04/06 | 2026/07/06 |  |  |  | USD | 103473.91 | 5443.47 | DAP | Site | Done | 2026/06/28
95 | HEY | CC815 | User 34 | Process | PR815213 | MAT53743 | 08/21/2026 | 09/07/2026 | COOLING TOWER FILL MEDIA REPLACEMENT | PO | Closed |  | Honeywell KSA | [5 empty] | EUR |  |  |  | Site | N/A
96 | FAV | CC665 | User 36 | Electrical | PR867219 | MAT91942 | 2026-05-01 | 2026-05-19 | COMPRESSOR OIL AND FILTER KIT | RFQ | Open | 4514182548 |  | 2026-05-26 |  |  | YES | 45 | SAR | 104486.38 | 3035.14 | CIF | Site
97 | FAV | CC406 | User 7 | INST | PR654889 | MAT22555 | 05/15/2026 | 06/03/2026 | PRESSURE TRANSMITTER HART PROTOCOL | On Hold | Open | 4514176205 | Siemens Arabia | 06/12/2026 | 09/03/2026 | 06/12/2026 |  | 45 | EUR | 47334.37 | 2496.24 | CIF | Site | Pending
98 | FAV | CC487 | User 7 | Utilities | PR984567 | MAT70540 | 01/01/2026 |  | PAINTING AND INSULATION CLADDING | PR | OPEN | [5 empty] | YES |  |  |  |  | DAP |  | N/A
99 | FAV | CC396 | User 4 | Mechanical | PR238221 | MAT35605 | 2026/06/01 | 2026/06/20 | HEAT EXCHANGER CLEANING SERVICE | RFQ | Open | 4514141982 | Siemens Arabia | 2026/06/30 |  | 2026/06/30 |  | 30 | EUR | 98388.42 | 4609.96 | CIF |  | Pending
100 | HEV | CC926 | User 26 | Utilities | PR861640 | MAT11560 | 2026/01/28 | 2026/02/03 | PAINTING AND INSULATION CLADDING | Cancelled | In Progress | 4514194593 | Endress+Hauser | 2026/03/01 | 2026/04/04 | 2026/03/01 | YES |  | EUR | 235112.37 | 7981.92 | DAP | Warehouse | pending
101 | HEY | CC524 | User 5 | Electrical | PR837781 | MAT11990 | 01-May-2026 | 13-May-2026 | CENTRIFUGAL PUMP MECHANICAL SEAL | PR | OPEN | 4514127775 | Endress+Hauser | 01-Jun-2026 | 07-Jul-2026 | 01-Jun-2026 | Yes | 60 |  | 240123.61 | 4931.25 | CIF | Site | Done | 11-Jul-2026
102 | HEV | CC237 | User 44 | Electrical | PR474267 | MAT21824 | 10/11/2025 |  | PRESSURE TRANSMITTER HART PROTOCOL | On Hold | Closed |  | Emerson Process |  |  |  | Yes | 45 |  |  |  | FOB | Port | N/A
103 | HEY | CC811 | User 21 | Utilities | PR234128 | MAT85063 | 08-Jul-2026 | 25-Jul-2026 | HAWKER WET CELL BATTERY SET 24V | PO | In Progress | 4514166766 | UNKNOWN VENDOR | 05-Aug-2026 | 30-Oct-2026 | 05-Aug-2026 |  | 30 | SAR | 24330.99 | 1739.06 |  | Port | pending
104 |  | CC289 | User 48 | Mechanical | PR332662 | MAT60059 | 26-Jun-2026 | 03-Jul-2026 | HAWKER WET CELL BATTERY SET 24V | PO | Open | 4514189487 | Siemens Arabia | 22-Jul-2026 | 27-Aug-2026 | 22-Jul-2026 |  | 90 | USD | 1701.63 | 72.38 |  | Site | Done | 24-Aug-2026
105 | HEY | CC839 | User 17 | Instrumentation | PR429840 | MAT51521 | 2026-03-24 | 2026-03-28 | LEVEL TRANSMITTER INSTALLATION | PO | In Progress | 4514188083 | SABIC Industrial | 2026-04-17 | 2026-07-17 | 2026-04-17 | No | 30 | EUR | 218528.88 | 11442.87 | FOB |  | pending
106 | HEY | CC214 | User 20 | Mechanical | PR871959 | MAT65368 | 06/11/2026 | 06/26/2026 | UPS BATTERY REPLACEMENT 110V | RFQ | OPEN | 4514169480 | Parker Hannifin | 06/30/2026 | 09/25/2026 |  | No |  | USD | 234012.03 | 14191.66 | DAP | Port
107 | FAV | CC605 | User 29 | Mechanical | PR529407 | MAT86566 | 2025/12/16 | 2025/12/24 | CENTRIFUGAL PUMP MECHANICAL SEAL |  |  |  | UNKNOWN VENDOR |  |  |  | No | 90 | EUR
108 | HEV | CC276 | User 45 | Process | PR306474 | MAT67848 | 09-May-2026 | 22-May-2026 | PRESSURE TRANSMITTER HART PROTOCOL |  | In Progress | 4514141080 | SKF Arabia | 16-Jun-2026 | 21-Sep-2026 | 16-Jun-2026 | YES |  | SAR |  |  | CIF | Warehouse | Pending
109 | FAV | CC105 | User 30 |  | PR882123 | MAT63456 | 05/04/2026 | 05/17/2026 | LABORATORY CHEMICALS AND REAGENTS | Cancelled | In Progress | 4514143897 | SABIC Industrial | 05/30/2026 | 07/19/2026 | 05/30/2026 | YES | 45 |  | 54669.04 | 4019.6 | DAP |  | pending
110 | HEY | CC410 | User 32 | Process | PR534905 | MAT68768 | 01/07/2026 | 01/21/2026 | FIRE DETECTION SYSTEM MAINTENANCE | RFQ | Closed | 4514174324 | GE Power Arabia | 02/15/2026 | 03/26/2026 | 02/15/2026 |  |  | USD | 209759.54 | 11989.64 | CIF | Site | pending
111 | FAV | CC190 | User 9 | MECH | PR292276 | MAT35304 | 12-Jun-2026 | 22-Jun-2026 | LABORATORY CHEMICALS AND REAGENTS | RFQ | OPEN |  | Saudi aramco supply | [5 empty] | SAR |  |  | CIF | Warehouse
112 | HEY | CC655 | User 31 | MECH | PR395562 | MAT98462 | 2026-08-21 |  | PROCESS ISOLATION WINDOW SIGHT GLASS |  | Closed |  | Yokogawa ME |  |  |  | Yes | 30 | EUR |  |  | FOB | Site
113 | FAV | CC178 | User 3 | Electrical | PR372416 | MAT52638 | 03/27/2026 | 04/01/2026 | COOLING TOWER FILL MEDIA REPLACEMENT | Delivered | OPEN | 4514138426 | Endress+Hauser | 04/21/2026 | 07/14/2026 |  | Yes |  | USD |  |  | DAP | Warehouse | Done | 07/26/2026
114 | HEY | CC401 | User 25 |  | PR428232 | MAT38346 | 2026/03/11 | 2026/03/15 | HEAT EXCHANGER CLEANING SERVICE | Delivered | Open | 4514152095 | Parker Hannifin | 2026/04/13 | 2026/07/23 |  | No | 30 |  | 30607.85 | 1776.38 | CIF | Site | Pending
115 | FAV | CC741 | User 16 | MECH | PR911483 | MAT71263 | 2026/08/11 | 2026/08/19 | SAFETY VALVE TESTING AND CALIBRATION |  | Open |  | Saudi aramco supply |  |  |  | No |  | USD |  |  | DAP | Site | Pending
116 | FAV | CC739 | User 28 |  | PR879351 | MAT81006 | 2026-03-24 |  | PROCESS ISOLATION WINDOW SIGHT GLASS | Cancelled | Open |  | Emerson Process |  |  |  | Yes | 60 | EUR |  |  | FOB | Warehouse
117 | HEV | CC708 | User 7 | INST | PR518049 | MAT82687 | 2026-03-20 |  | COOLING TOWER FILL MEDIA REPLACEMENT | RFQ |  |  | SKF Arabia |  |  |  | YES | 30 | EUR |  |  | CIF | Site
118 | FAV | CC286 | User 36 | MECH | PR373198 | MAT27100 |  | 17-Aug-2026 | CONTROL VALVE ACTUATOR REPAIR | RFQ | OPEN |  | Siemens Arabia |  |  |  | No | 60 |  |  |  | CIF |  | N/A
119 | HEY | CC205 | User 46 | MECH | PR222861 | MAT91726 | 31-Jul-2026 |  | COMPRESSOR OIL AND FILTER KIT | Delivered | OPEN |  | SABIC INDUSTRIAL |  |  |  |  | 30 |  |  |  | CIF | Port
120 | FAV | CC559 | User 49 |  | PR752970 | MAT93833 | 02/08/2026 | 22/08/2026 | PLC SPARE PARTS AND MODULES |  |  | 4514118047 | SABIC Industrial | 12/09/2026 | 19/12/2026 |  | Yes | 90 | EUR | 145693.7 | 6141.81 | FOB | Site
121 | HEV | CC968 | User 7 | Mechanical | PR749454 | MAT68556 | 01/28/2026 |  | UPS BATTERY REPLACEMENT 110V | Delivered |  |  | Saudi Aramco Supply |  |  |  | YES | 90 | EUR |  |  | CIF | Site
122 | HEY | CC439 | User 10 | Mechanical | PR413166 | MAT56863 | 21/07/2026 | 04/08/2026 | HAWKER WET CELL BATTERY SET 24V | On Hold | Closed | 4514139997 | Parker Hannifin | 31/08/2026 | 07/10/2026 | 31/08/2026 | Yes | 45 | USD |  |  |  | Warehouse | In Transit
123 | FAV | CC947 | User 11 | Mechanical | PR604489 | MAT26996 | 01/16/2026 | 02/05/2026 | LEVEL TRANSMITTER INSTALLATION | PR |  | 4514116712 | Parker Hannifin | 03/01/2026 | 06/05/2026 | 03/01/2026 | No | 60 | SAR |  |  | DAP | Warehouse | Delivered | 06/19/2026
124 | HEV | CC256 | User 11 | Process | PR742916 | MAT53122 | 30/06/2026 |  | ELECTRICAL CABLE 3CX16MM ARMOURED | RFQ | OPEN |  | Schneider Electric KSA |  |  |  |  | 30 |  |  |  | CIF
125 | HEY | CC739 | User 22 | Civil | PR672231 | MAT73160 | 2026-08-10 | 2026-08-27 | PROCESS ISOLATION WINDOW SIGHT GLASS |  | Closed | 4514147900 | Saudi aramco supply | 2026-09-11 | 2026-10-09 |  | No |  |  | 149012.28 | 6594.32 | DAP |  | Pending
126 | HEY | CC512 | User 15 | Electrical | PR502454 | MAT56127 | 04/07/2026 | 10/07/2026 | HAWKER WET CELL BATTERY SET 24V | PO | Closed | 4514199317 | Emerson Process | 08/08/2026 | 28/08/2026 | 08/08/2026 |  | 60 | EUR |  |  | DAP | Site | In Transit
127 | FAV | CC795 | User 24 | Instrumentation | PR584725 | MAT27862 | 28-Apr-2026 | 08-May-2026 | LEVEL TRANSMITTER INSTALLATION | PO |  | 4514174210 | Saudi aramco supply | 21-May-2026 | 22-Aug-2026 | 21-May-2026 |  | 90 | SAR | 123617.83 | 9057.92 | FOB | Warehouse | Pending
128 |  | CC549 | User 40 | Electrical | PR138639 | MAT72622 | 2026/07/18 |  | SCAFFOLDING ERECTION AND DISMANTLING | [7 empty] | Yes | 90 | SAR |  |  | FOB |  | Pending
129 | FAV | CC268 | User 6 | Instrumentation | PR831297 | MAT36621 | 05/17/2026 | 05/23/2026 | LEVEL TRANSMITTER INSTALLATION | RFQ |  | 4514176813 | Saudi aramco supply | 06/09/2026 |  |  | No | 90 |  | 113579 | 2872.78 |  | Warehouse | N/A
130 |  | CC881 | User 46 | INST | PR848922 | MAT49237 | 2026/01/15 | 2026/01/25 | SCAFFOLDING ERECTION AND DISMANTLING | Delivered | OPEN | 4514158412 | Al-Rushaid Trading Co. | 2026/02/07 | 2026/03/31 |  | Yes |  | USD | 174183.8 | 6234.79 | FOB | Warehouse | Delivered | 2026/04/14
131 | HEV | CC745 | User 43 | Electrical | PR835671 | MAT90053 | 03-Feb-2026 | 20-Feb-2026 | HAWKER WET CELL BATTERY SET 24V | On Hold | OPEN | 4514141338 | Endress+Hauser | 27-Feb-2026 | 03-Apr-2026 | 27-Feb-2026 |  | 60 | SAR | 217264.53 | 5476 | CIF | Site
132 | FAV | CC161 | User 11 | Mechanical | PR402020 | MAT71740 | 02/18/2026 | 03/01/2026 | PRESSURE TRANSMITTER HART PROTOCOL | PO | In Progress | 4514165311 |  | 03/10/2026 | 03/25/2026 | 03/10/2026 | No | 60 |  | 80591.65 | 2302 | DAP |  | pending
133 | HEV | CC379 | User 9 | Electrical | PR527150 | MAT98821 | 2026/07/28 |  | UPS BATTERY REPLACEMENT 110V | PO | Closed |  | Parker Hannifin |  |  |  | No | 45 |  |  |  | CIF | Site | N/A
134 | HEY | CC637 | User 47 | MECH | PR954236 | MAT95781 | 24-Jul-2026 | 02-Aug-2026 | PROCESS ISOLATION WINDOW SIGHT GLASS | PO | In Progress | 4514170563 | SABIC INDUSTRIAL | 13-Aug-2026 | 07-Oct-2026 | 13-Aug-2026 |  | 45 | USD |  |  | FOB | Site | In Transit
135 | HEY | CC786 | User 30 | Electrical | PR468599 | MAT56016 | 2026-07-22 |  | HAWKER WET CELL BATTERY SET 24V | Cancelled | OPEN |  | ABB Saudi Arabia |  |  |  | Yes |  |  |  |  | CIF | Site | Pending
136 | FAV | CC909 | User 25 | Utilities | PR325503 | MAT27138 | 2025/11/26 | 2025/12/13 | PROCESS ISOLATION WINDOW SIGHT GLASS |  | OPEN | 4514124244 | Parker Hannifin | 2025/12/29 |  | 2025/12/29 | No | 30 |  | 101596.86 | 7079.28 |  |  | Pending
137 | HEY | CC458 | User 37 | MECH | PR309682 | MAT80041 | 27-Jun-2026 | 15-Jul-2026 | LABORATORY CHEMICALS AND REAGENTS | Cancelled | Open | 4514148557 | ABB Saudi Arabia | 18-Jul-2026 | 07-Sep-2026 |  | YES | 90 | SAR | 158380.69 | 7306.99 | CIF | Site
138 | FAV | CC795 | User 4 | Civil | PR979967 | MAT84779 | 20/03/2026 |  | PROCESS ISOLATION WINDOW SIGHT GLASS | PR | In Progress |  | Saudi Aramco Supply |  |  |  | Yes |  | USD |  |  | DAP
139 | FAV | CC504 | User 1 | Mechanical | PR453995 | MAT40082 | 2026-07-11 | 2026-07-28 | FLOWMETER CALIBRATION AND CERTIFICATION | Delivered | In Progress | 4514188148 |  | 2026-08-23 | 2026-10-24 |  | Yes | 90 | EUR | 147190.9 | 3347.42 | DAP |  | pending
140 | HEY | CC916 | User 30 | Civil | PR393965 | MAT35227 | 2025-11-11 |  | GATE VALVE 6 INCH CLASS 300 | RFQ | Closed |  | Parker Hannifin |  |  |  |  | 90 |  |  |  | DAP | Site | Pending
141 | HEY | CC460 | User 2 | INST | PR329845 | MAT28446 | 24/07/2026 | 29/07/2026 | ANNUAL PM SERVICE FOR CHILLER UNIT | PO | OPEN | 4514172311 | Saudi Aramco Supply | 25/08/2026 | 30/11/2026 |  | YES | 45 | EUR | 16074.28 | 722.96 | FOB |  | In Transit
142 | FAV | CC291 | User 46 | Utilities | PR307712 | MAT49828 | 2025/11/18 | 2025/12/05 | ANNUAL PM SERVICE FOR CHILLER UNIT | RFQ |  | 4514188959 | Honeywell KSA | 2025/12/26 | 2026/01/11 | 2025/12/26 |  | 60 |  | 230098.75 | 16378.82 | DAP | Port | Pending
143 | HEY | CC292 | User 24 | Mechanical | PR787608 | MAT62514 | 08/12/2025 | 13/12/2025 | HAWKER WET CELL BATTERY SET 24V | Delivered | Closed | 4514143221 | Saudi aramco supply | 20/12/2025 | 20/03/2026 |  |  |  | EUR | 89408.39 | 4315.08 | FOB | Site
144 | HEY | CC281 | User 4 | Utilities | PR333409 | MAT84765 | 2026/07/31 | 2026/08/18 | GATE VALVE 6 INCH CLASS 300 | PR | Closed | 4514150411 | Parker Hannifin | 2026/08/22 | 2026/12/11 |  |  | 90 | USD | 87555.66 | 5879.91 | FOB |  | In Transit
145 | FAV | CC260 | User 33 | Instrumentation | PR181748 | MAT86145 | 20/03/2026 | 24/03/2026 | ELECTRICAL CABLE 3CX16MM ARMOURED | PO | Open | 4514186323 | UNKNOWN VENDOR | 27/03/2026 | 16/04/2026 | 27/03/2026 |  |  | SAR | 170560.13 | 9380.28 | FOB | Warehouse | Delivered | 08/04/2026
146 | HEY | CC603 | User 9 | Civil | PR915210 | MAT30797 | 2025-11-08 |  | CENTRIFUGAL PUMP MECHANICAL SEAL |  | OPEN | [6 empty] | 90 |  |  |  | FOB
147 | HEY | CC258 | User 7 | Electrical | PR828339 | MAT91971 | 05/03/2026 | 05/23/2026 | PAINTING AND INSULATION CLADDING | Cancelled |  | 4514113101 | Siemens Arabia | 06/01/2026 | 07/02/2026 | 06/01/2026 | No | 30 |  | 75089.91 | 4290.47 | DAP | Port | In Transit
148 | FAV | CC182 | User 17 | Civil | PR643813 | MAT40619 | 2026-03-25 | 2026-04-14 | COOLING TOWER FILL MEDIA REPLACEMENT | PR | OPEN | 4514189774 | Al Mojil Group | 2026-05-11 | 2026-08-01 | 2026-05-11 | Yes | 30 | USD | 32205.34 | 1289.96 |  |  | Pending
149 | HEY | CC841 | User 1 | Mechanical | PR724654 | MAT36104 | 2026/05/31 |  | PRESSURE TRANSMITTER HART PROTOCOL | RFQ | Closed |  | SABIC Industrial |  |  |  | YES | 30 | USD |  |  | FOB | Port
150 | HEY | CC224 | User 48 | Process | PR293751 | MAT80320 | 2025-12-10 | 2025-12-29 | HAWKER WET CELL BATTERY SET 24V | On Hold | OPEN | [5 empty] | YES | 45 | USD |  |  | DAP | Port | Pending
151 | HEV | CC700 | User 21 | Utilities | PR330822 | MAT58457 |  | 12-Jul-2026 | PLC SPARE PARTS AND MODULES |  |  | 4514178639 |  | 22-Jul-2026 |  | 22-Jul-2026 | Yes |  | EUR | 117360.44 | 3930.87 | FOB
152 | FAV | CC941 | User 43 | INST | PR988021 | MAT35270 | 15/05/2026 | 20/05/2026 | UPS BATTERY REPLACEMENT 110V | PR | Open | 4514162833 | ABB Saudi Arabia | 29/05/2026 | 14/06/2026 | 29/05/2026 | No |  |  | 25893.59 | 1294.09 | DAP | Warehouse | Done | 15/06/2026
153 | HEY | CC544 | User 37 | MECH | PR640530 | MAT42484 | 27-Nov-2025 | 03-Dec-2025 | HAWKER WET CELL BATTERY SET 24V | On Hold | In Progress | 4514199012 | UNKNOWN VENDOR | 22-Dec-2025 | 07-Apr-2026 | 22-Dec-2025 | Yes | 60 | EUR | 48068.98 | 3250.28 |  | Port | Pending
154 | HEY | CC884 | User 40 | Electrical | PR326197 | MAT39250 | 03/08/2026 |  | ELECTRICAL CABLE 3CX16MM ARMOURED | Cancelled |  |  | Al Mojil Group |  |  |  | YES | 60 |  |  |  | DAP | Site | Pending
155 |  | CC908 | User 17 |  | PR201310 | MAT15785 | 2026-07-01 | 2026-07-10 | COOLING TOWER FILL MEDIA REPLACEMENT | PO | Closed |  | ABB Saudi Arabia |  |  |  |  | 60 | SAR |  |  |  | Port | Pending
156 | FAV | CC238 | User 35 | Civil | PR676887 | MAT54603 | 16/05/2026 | 27/05/2026 | CONTROL VALVE ACTUATOR REPAIR | Cancelled | In Progress | 4514176598 | SABIC Industrial | 04/06/2026 | 24/09/2026 |  |  | 45 | EUR | 242255.76 | 5397.66 | DAP | Warehouse | pending
157 | FAV | CC742 | User 7 | Utilities | PR386388 | MAT36979 | 03/02/2026 | 03/15/2026 | FLOWMETER CALIBRATION AND CERTIFICATION | PR | OPEN | 4514177122 | Al Mojil Group | 03/24/2026 | 05/18/2026 |  | Yes | 60 | USD | 81719.83 | 2076.44 | DAP |  | Partial Delivery
158 | HEY | CC121 | User 23 | INST | PR795223 | MAT38062 | 24-Apr-2026 | 07-May-2026 | FIRE DETECTION SYSTEM MAINTENANCE | RFQ | In Progress | 4514152935 | Saudi aramco supply | 18-May-2026 |  |  |  | 90 | EUR | 8845.92 | 210.26 | DAP | Port
159 | FAV | CC960 | User 13 | Civil | PR614378 | MAT22489 | 2025/12/12 |  | GATE VALVE 6 INCH CLASS 300 | On Hold | Closed |  | Saudi aramco supply |  |  |  |  | 60 | USD |  |  |  | Site | Pending
160 | HEY | CC750 | User 41 | MECH | PR668370 | MAT39255 | 2025/12/03 |  | ELECTRICAL CABLE 3CX16MM ARMOURED |  | OPEN |  | Parker Hannifin |  |  |  | YES | 45 | USD |  |  | CIF | Site
161 | HEY | CC534 | User 24 | INST | PR763918 | MAT18537 | 2025-12-25 | 2026-01-12 | PROCESS ISOLATION WINDOW SIGHT GLASS |  | OPEN | 4514147062 | Parker Hannifin | 2026-02-06 | 2026-05-13 | 2026-02-06 | YES | 45 | USD | 51089.78 | 1806.94 | FOB | Warehouse | Del | 2026-05-19
162 | HEY | CC817 | User 46 | Electrical | PR809652 | MAT44368 | 2026/03/11 |  | COMPRESSOR OIL AND FILTER KIT |  | Closed |  | Siemens Arabia |  |  |  | Yes | 90 | USD |  |  | CIF | Warehouse
163 | HEY | CC367 | User 37 | Utilities | PR496996 | MAT63187 |  |  | CONTROL VALVE ACTUATOR REPAIR | Cancelled |  |  | SABIC INDUSTRIAL |  |  |  | YES | 90 | EUR |  |  | DAP
164 | FAV | CC884 | User 8 | Mechanical | PR656258 | MAT21532 | 01/23/2026 | 01/29/2026 | COMPRESSOR OIL AND FILTER KIT | Delivered | Closed | [5 empty] | YES | 45 | EUR |  |  | CIF
165 | HEY | CC550 | User 1 | Process | PR364008 | MAT10229 | 2026-05-14 | 2026-05-22 | FIRE DETECTION SYSTEM MAINTENANCE | RFQ | Closed | 4514198761 | Saudi Aramco Supply | 2026-06-19 |  | 2026-06-19 |  | 60 |  | 148904.58 | 9044.48 |  |  | Pending
166 | HEY | CC952 | User 34 | Utilities | PR988259 | MAT85680 | 13-Feb-2026 |  | HEAT EXCHANGER CLEANING SERVICE | RFQ | OPEN |  | Siemens Arabia |  |  |  | YES | 45 | SAR |  |  | FOB | Warehouse
167 |  | CC198 | User 19 | Process | PR627058 | MAT69478 | 10/02/2026 | 14/02/2026 | SCAFFOLDING ERECTION AND DISMANTLING | PO |  | 4514144906 | Saudi Aramco Supply | 26/02/2026 | 26/04/2026 |  | Yes | 90 | USD | 205159.92 | 9067.42 | DAP |  | delivered | 21/04/2026
168 | HEV | CC357 | User 18 | Civil | PR792620 | MAT18687 | 21/12/2025 | 07/01/2026 | SCAFFOLDING ERECTION AND DISMANTLING | Delivered |  | 4514113812 | Honeywell KSA | 18/01/2026 | 24/04/2026 | 18/01/2026 | No | 45 | SAR | 32712.73 | 1993.94 | CIF | Port | Delivered | 09/05/2026
169 | HEV | CC663 | User 11 | Civil | PR883767 | MAT64756 | 02/05/2026 | 02/13/2026 | COOLING TOWER FILL MEDIA REPLACEMENT | RFQ | Open |  | Al-Rushaid Trading Co. |  |  |  | No | 90 |  |  |  | FOB | Port
170 | FAV | CC640 | User 45 | Utilities | PR422202 | MAT32678 | 2025-11-16 |  | LEVEL TRANSMITTER INSTALLATION | PR |  |  | Yokogawa ME |  |  |  | No | 90 | USD |  |  | DAP | Site
171 | HEV | CC662 | User 27 |  | PR273438 | MAT29924 | 22/07/2026 | 31/07/2026 | FIRE DETECTION SYSTEM MAINTENANCE | Delivered | Closed | 4514138584 | GE Power Arabia | 10/08/2026 |  | 10/08/2026 | No | 90 | SAR | 1427.75 | 53.94 | CIF | Port | N/A
172 | HEY | CC382 | User 26 | Process | PR313493 | MAT90932 | 04/16/2026 |  | COOLING TOWER FILL MEDIA REPLACEMENT | Cancelled | In Progress |  | Emerson Process |  |  |  | Yes | 90 | USD |  |  | CIF | Port | N/A
173 | FAV | CC681 | User 28 | Process | PR273361 | MAT14156 | 2026/05/01 |  | HAWKER WET CELL BATTERY SET 24V | Cancelled | OPEN |  | Al-Rushaid Trading Co. |  |  |  | No |  | EUR |  |  |  | Site | N/A
174 |  | CC690 | User 28 |  | PR720589 | MAT54955 | 2026-02-26 | 2026-03-07 | LABORATORY CHEMICALS AND REAGENTS |  | OPEN | 4514116789 | Schneider Electric KSA | 2026-04-01 |  | 2026-04-01 |  | 45 | EUR | 223112.35 | 8092.89 | FOB | Port | N/A
175 | HEY | CC828 | User 38 | Utilities | PR979760 | MAT89166 | 2026/04/18 |  | GATE VALVE 6 INCH CLASS 300 | PO |  |  | Yokogawa ME |  |  |  | Yes | 45 |  |  |  | CIF
176 | HEY | CC335 | User 8 | MECH | PR332757 | MAT93205 | 12/21/2025 | 01/10/2026 | UPS BATTERY REPLACEMENT 110V | PR | In Progress |  | Al-Rushaid Trading Co. |  |  |  | No |  | EUR |  |  | FOB | Warehouse | Pending
177 | HEV | CC666 | User 3 | MECH | PR384484 | MAT68227 | 2026-05-22 |  | PROCESS ISOLATION WINDOW SIGHT GLASS | On Hold |  |  | Honeywell KSA |  |  |  |  | 90 |  |  |  |  | Port | Pending
178 | HEY | CC289 | User 32 | Mechanical | PR144657 | MAT63905 | 06/15/2026 | 07/04/2026 | UPS BATTERY REPLACEMENT 110V | PR | OPEN | 4514189664 | Al Mojil Group | 08/03/2026 | 11/20/2026 |  | Yes | 45 | SAR | 156114.79 | 3932.87 | CIF | Port | In Transit
179 |  | CC187 | User 16 | Instrumentation | PR379761 | MAT75947 | 2026-06-16 |  | FLOWMETER CALIBRATION AND CERTIFICATION | RFQ | Open |  | Endress+Hauser |  |  |  |  | 60 | EUR |  |  |  | Warehouse
180 | FAV | CC749 | User 8 | Civil | PR163441 | MAT73684 | 12-Feb-2026 | 18-Feb-2026 | FLOWMETER CALIBRATION AND CERTIFICATION | PR | Open | 4514170980 | ABB Saudi Arabia | 23-Feb-2026 | 19-Jun-2026 | 23-Feb-2026 | Yes | 45 | SAR | 20299.34 | 1469.37 |  | Site | In Transit
181 | FAV | CC192 | User 37 | INST | PR218678 | MAT94737 | 2026-01-19 | 2026-02-07 | LEVEL TRANSMITTER INSTALLATION | On Hold | OPEN | 4514183894 | SKF Arabia | 2026-02-16 |  |  | Yes | 90 |  | 170431.91 | 7638.33 | DAP | Warehouse
182 | HEV | CC234 | User 1 | Utilities | PR613127 | MAT37277 | 13-May-2026 |  | PAINTING AND INSULATION CLADDING | [7 empty] | No | 45 | USD |  |  |  | Port
183 | HEV | CC941 | User 49 | Instrumentation | PR115916 | MAT87391 | 06/02/2026 | 06/15/2026 | PAINTING AND INSULATION CLADDING |  | Closed |  | Yokogawa ME | [5 empty] | SAR |  |  |  | Warehouse
184 | FAV | CC266 | User 47 | Process | PR585855 | MAT98299 | 03/15/2026 | 03/26/2026 | SAFETY VALVE TESTING AND CALIBRATION | PR | OPEN | 4514186109 | Al Mojil Group | 04/08/2026 | 07/12/2026 | 04/08/2026 | No | 30 | EUR | 229966.13 | 4949.75 | FOB | Port | pending
185 | HEY | CC291 | User 3 | Mechanical | PR601228 | MAT72589 | 2026/05/23 | 2026/05/29 | HEAT EXCHANGER CLEANING SERVICE | PO |  | 4514173721 |  | 2026/06/01 | 2026/09/28 |  | Yes |  | SAR |  |  | CIF |  | Pending
186 | HEY | CC867 | User 23 | Instrumentation | PR151077 | MAT96542 | 11/12/2025 | 15/12/2025 | COMPRESSOR OIL AND FILTER KIT | On Hold | In Progress | 4514144042 | Schneider Electric KSA | 08/01/2026 | 28/02/2026 |  |  | 30 | SAR | 230139.49 | 8358.14 | CIF |  | Partial Delivery
187 | HEY | CC814 | User 46 | MECH | PR350035 | MAT88571 | 2026-07-25 | 2026-08-03 | SAFETY VALVE TESTING AND CALIBRATION | PO | Closed | 4514199806 | Yokogawa ME | 2026-08-27 | 2026-09-23 | 2026-08-27 | YES | 60 | USD | 137090.35 | 4666.45 | CIF | Warehouse
188 | HEY | CC729 | User 40 | Instrumentation | PR911020 | MAT63125 | 2026/03/01 | 2026/03/10 | LEVEL TRANSMITTER INSTALLATION | RFQ | In Progress |  | Yokogawa ME |  |  |  | Yes | 45 | EUR |  |  | FOB | Warehouse | Pending
189 |  | CC753 | User 38 | Mechanical | PR672014 | MAT57711 | 22/03/2026 | 07/04/2026 | PAINTING AND INSULATION CLADDING | PO | OPEN | 4514133623 | Al Mojil Group | 21/04/2026 | 11/08/2026 | 21/04/2026 |  | 60 | EUR | 174654.53 | 7729.71 | DAP | Port | delivered | 11/08/2026
190 | HEY | CC327 | User 30 | Utilities | PR241122 | MAT99284 | 06/02/2026 | 06/06/2026 | FIRE DETECTION SYSTEM MAINTENANCE | On Hold |  | 4514162550 | SKF Arabia | 07/01/2026 |  | 07/01/2026 | No |  | USD | 80180.05 | 3646.38 |  | Site
191 | HEY | CC725 | User 10 | Mechanical | PR240279 | MAT81773 |  | 2026/01/12 | HEAT EXCHANGER CLEANING SERVICE |  | In Progress |  | Endress+Hauser |  |  |  | Yes | 90 | EUR |  |  | CIF | Port | N/A
192 | HEY | CC937 | User 23 | Utilities | PR554037 | MAT98775 | 2026/05/14 | 2026/05/22 | PAINTING AND INSULATION CLADDING | RFQ | Open | 4514118889 | Yokogawa ME | 2026/06/03 | 2026/08/30 |  |  | 45 | SAR | 51509.36 | 2532.21 |  | Port | pending
193 | HEY | CC976 | User 30 | MECH | PR362769 | MAT77126 | 21-Mar-2026 | 01-Apr-2026 | HEAT EXCHANGER CLEANING SERVICE | Delivered | OPEN | 4514127333 | Honeywell KSA | 05-Apr-2026 | 14-Jun-2026 | 05-Apr-2026 | No | 30 |  | 35116.99 | 2355.99 | CIF |  | Pending
194 |  | CC473 | User 19 | MECH | PR781642 | MAT96433 | 21/11/2025 | 26/11/2025 | SCAFFOLDING ERECTION AND DISMANTLING | Delivered | Open | 4514161573 | Parker Hannifin | 23/12/2025 | 21/02/2026 | 23/12/2025 |  | 45 | EUR |  |  |  | Warehouse | Del | 05/03/2026
195 | HEY | CC162 | User 5 | Process | PR207910 | MAT24482 | 2026-04-30 |  | ANNUAL PM SERVICE FOR CHILLER UNIT |  | Closed |  | SABIC INDUSTRIAL |  |  |  | Yes |  |  |  |  | CIF | Port | N/A
196 | HEY | CC796 | User 50 | Process | PR199554 | MAT18357 | 07/16/2026 |  | ELECTRICAL CABLE 3CX16MM ARMOURED | PO | Closed |  | Emerson Process |  |  |  |  | 90 | USD |  |  | CIF | Warehouse | Pending
197 |  | CC929 | User 26 | Civil | PR151051 | MAT98405 | 12/22/2025 | 01/10/2026 | FLOWMETER CALIBRATION AND CERTIFICATION | PR | Closed | 4514131349 | ABB Saudi Arabia | 02/05/2026 | 05/20/2026 | 02/05/2026 |  | 90 | EUR | 189639.51 | 5967.82 | CIF | Site | Del | 05/30/2026
198 | HEY | CC109 | User 15 | Mechanical | PR362906 | MAT98658 | 2026-03-24 | 2026-04-07 | SCAFFOLDING ERECTION AND DISMANTLING |  | Closed | 4514145048 | Schneider Electric KSA | 2026-04-19 | 2026-05-23 | 2026-04-19 |  |  | USD | 217838.29 | 6844.45 | FOB | Warehouse | Partial Delivery
199 | HEY | CC862 | User 4 | Instrumentation | PR936923 | MAT82599 | 2026-01-27 | 2026-02-08 | SCAFFOLDING ERECTION AND DISMANTLING | PR | In Progress | 4514199547 | Al-Rushaid Trading Co. | 2026-03-05 | 2026-05-01 | 2026-03-05 |  | 90 | SAR |  |  | FOB |  | pending
200 | HEY | CC968 | User 43 |  | PR515130 | MAT91391 | 2026/05/22 |  | PAINTING AND INSULATION CLADDING | Delivered | Open | [5 empty] | YES | 60 | USD |  |  |  | Warehouse | Pending
201 | HEY | CC606 | User 30 | Utilities | PR682526 | MAT82668 | 07/26/2026 | 08/05/2026 | HAWKER WET CELL BATTERY SET 24V | RFQ | In Progress | 4514142154 | Honeywell KSA | 08/21/2026 |  | 08/21/2026 | Yes | 90 |  | 131847.15 | 8314.59 |  | Warehouse | N/A
202 | HEY | CC633 | User 8 | MECH | PR670857 | MAT45332 | 2026/04/15 |  | ANNUAL PM SERVICE FOR CHILLER UNIT | Delivered |  |  | Saudi Aramco Supply | [5 empty] | SAR |  |  | DAP | Port
203 | HEY | CC386 | User 45 | Electrical | PR628685 | MAT76276 | 2026-03-27 |  | SAFETY VALVE TESTING AND CALIBRATION | PO | Closed | [6 empty] | 90 | USD |  |  | DAP
204 | HEV | CC164 | User 41 | Electrical | PR700539 | MAT16702 | 2026/02/06 | 2026/02/24 | ANNUAL PM SERVICE FOR CHILLER UNIT | Cancelled | In Progress | 4514115782 | Honeywell KSA | 2026/03/05 | 2026/05/25 |  | YES | 60 | SAR | 197286.63 | 8697.52 | FOB | Site | In Transit
205 |  | CC136 | User 6 | Instrumentation | PR144355 | MAT70759 | 03/02/2026 | 03/21/2026 | COMPRESSOR OIL AND FILTER KIT | Delivered | Closed | 4514175300 | Saudi aramco supply | 03/26/2026 |  | 03/26/2026 | Yes | 90 | SAR | 51267.1 | 2576.33 | CIF
206 | FAV | CC631 | User 33 | Utilities | PR722824 | MAT80307 | 01/07/2026 | 01/12/2026 | GATE VALVE 6 INCH CLASS 300 | PO | Open | 4514119281 | Yokogawa ME | 01/20/2026 | 05/17/2026 | 01/20/2026 | Yes | 30 | SAR | 161673.93 | 7123.83 |  | Site | Delivered | 05/20/2026
207 | HEV | CC529 | User 12 | Process | PR971793 | MAT19280 | 09-Mar-2026 |  | GATE VALVE 6 INCH CLASS 300 | PR | Closed |  | Siemens Arabia |  |  |  | YES | 90 | USD |  |  |  | Warehouse | Pending
208 | HEY | CC238 | User 23 | Process | PR275561 | MAT24513 | 2026/02/02 | 2026/02/09 | PAINTING AND INSULATION CLADDING | RFQ | Open | 4514194035 | Honeywell KSA | 2026/02/19 | 2026/06/14 | 2026/02/19 |  | 30 | SAR |  |  | FOB | Site | In Transit
209 | HEV | CC646 | User 20 | MECH | PR491858 | MAT37713 | 2025/12/22 | 2025/12/30 | ANNUAL PM SERVICE FOR CHILLER UNIT | PO | Closed | 4514190379 | Schneider Electric KSA | 2026/01/09 | 2026/02/15 | 2026/01/09 | Yes | 45 |  | 73120.2 | 4211.42 |  | Warehouse | Del | 2026/02/22
210 | FAV | CC968 | User 43 | Instrumentation | PR455849 | MAT21240 | 07/20/2026 | 08/04/2026 | FLOWMETER CALIBRATION AND CERTIFICATION | Delivered | OPEN | 4514128706 | Al-Rushaid Trading Co. | 08/11/2026 | 09/28/2026 |  |  | 90 | SAR | 134330.04 | 9433.99 | DAP | Port
211 | FAV | CC980 | User 35 | Mechanical | PR619827 | MAT87413 | 2026-04-27 | 2026-05-02 | CONTROL VALVE ACTUATOR REPAIR | Cancelled |  | 4514188317 | SABIC INDUSTRIAL | 2026-05-22 |  | 2026-05-22 | YES |  | SAR | 28557.63 | 810.55 | CIF
212 | HEY | CC403 | User 24 | MECH | PR731059 | MAT98828 | 2026-03-30 | 2026-04-16 | LABORATORY CHEMICALS AND REAGENTS | RFQ | Closed | 4514167652 | ABB Saudi Arabia | 2026-05-11 | 2026-09-04 | 2026-05-11 |  | 45 | USD | 134208.77 | 4877.5 | CIF | Site | In Transit
213 | HEY | CC661 | User 40 | MECH | PR529405 | MAT39567 | 2026-07-18 | 2026-07-28 | COMPRESSOR OIL AND FILTER KIT | Delivered |  | 4514115591 | Yokogawa ME | 2026-08-02 | 2026-08-22 | 2026-08-02 | YES | 90 | SAR | 11967.31 | 616.37 |  |  | Del | 2026-08-15
214 | HEY | CC934 | User 1 | MECH | PR515762 | MAT28753 | 2026/03/09 |  | ELECTRICAL CABLE 3CX16MM ARMOURED | Delivered | In Progress |  | Endress+Hauser |  |  |  |  | 30 | EUR |  |  |  | Port | Pending
215 | HEY | CC958 | User 25 | INST | PR860563 | MAT27417 | 2026-07-25 | 2026-07-28 | LABORATORY CHEMICALS AND REAGENTS |  | Closed | 4514161153 | Al Mojil Group | 2026-08-25 | 2026-12-10 | 2026-08-25 |  |  | USD | 55195.88 | 3963.62 | CIF | Site
216 | FAV | CC866 | User 13 | Mechanical | PR813629 | MAT36973 | 2026-01-06 | 2026-01-15 | PROCESS ISOLATION WINDOW SIGHT GLASS | PO | In Progress | 4514161279 | Parker Hannifin | 2026-01-22 | 2026-02-27 | 2026-01-22 |  |  | USD | 74460.63 | 2654.15 |  | Port | Pending
217 | HEY | CC213 | User 42 | INST | PR760123 | MAT98478 | 2026-03-26 | 2026-03-31 | HAWKER WET CELL BATTERY SET 24V |  | OPEN | 4514194193 | Al-Rushaid Trading Co. | 2026-04-21 | 2026-08-07 |  |  | 90 |  | 219530.25 | 16702.88 | DAP | Site | Pending
218 | FAV | CC215 | User 42 | Utilities | PR275374 | MAT12449 | 2026/03/21 |  | PRESSURE TRANSMITTER HART PROTOCOL |  | OPEN |  | Saudi aramco supply |  |  |  |  | 90 | SAR
219 | FAV | CC831 | User 24 | INST | PR773193 | MAT10344 | 26-Mar-2026 |  | FIRE DETECTION SYSTEM MAINTENANCE | RFQ | Closed |  | Siemens Arabia |  |  |  |  | 60 | USD |  |  | FOB | Port | N/A
220 | HEY | CC511 | User 21 | Electrical | PR681384 | MAT83152 | 09/02/2026 |  | FLOWMETER CALIBRATION AND CERTIFICATION | PR |  |  | Saudi Aramco Supply | [5 empty] | EUR |  |  |  | Site | Pending
221 | HEV | CC270 | User 39 | Civil | PR399389 | MAT57947 | 01/11/2025 | 20/11/2025 | PLC SPARE PARTS AND MODULES | Delivered | Closed | 4514118260 | GE Power Arabia | 02/12/2025 | 04/01/2026 | 02/12/2025 | Yes | 45 | EUR | 7259.12 | 525.98 | DAP |  | Pending
222 | FAV | CC830 | User 38 | Utilities | PR830761 | MAT27544 | 23-Dec-2025 |  | ANNUAL PM SERVICE FOR CHILLER UNIT | On Hold | [6 empty] | Yes | 90 | USD |  |  | CIF | Warehouse
223 | HEY | CC758 | User 1 | Instrumentation | PR107665 | MAT99226 | 08/01/2026 | 17/01/2026 | ANNUAL PM SERVICE FOR CHILLER UNIT | PR |  | 4514171070 | Emerson Process | 10/02/2026 | 17/04/2026 | 10/02/2026 | No |  | SAR | 60960.12 | 3733.53 |  | Site | Done | 29/04/2026
224 | FAV | CC475 | User 11 | Civil | PR406420 | MAT11197 | 05/04/2026 | 09/04/2026 | PLC SPARE PARTS AND MODULES | PR |  | 4514142247 |  | 19/04/2026 | 03/05/2026 | 19/04/2026 |  | 60 |  | 182906.94 | 12059.58 | CIF
225 |  | CC328 | User 45 | Electrical | PR198020 | MAT60575 | 2026-08-11 | 2026-08-14 | FIRE DETECTION SYSTEM MAINTENANCE | PR | Open | 4514185463 | Parker Hannifin | 2026-09-12 | 2026-12-25 |  |  | 30 | SAR | 40845.35 | 1731.19 | FOB | Site | pending
226 | FAV | CC581 | User 31 | Process | PR983159 | MAT70053 | 23/12/2025 | 02/01/2026 | CENTRIFUGAL PUMP MECHANICAL SEAL | Cancelled |  |  | Yokogawa ME |  |  |  | Yes |  |  |  |  | DAP | Warehouse
227 | HEV | CC596 | User 42 | Utilities | PR639185 | MAT78108 | 15-Aug-2026 |  | PROCESS ISOLATION WINDOW SIGHT GLASS | Cancelled |  |  | Al-Rushaid Trading Co. |  |  |  | No | 90 | EUR |  |  | CIF | Port | Pending
228 | HEY | CC306 | User 37 |  | PR620018 | MAT82260 | 29/06/2026 |  | LEVEL TRANSMITTER INSTALLATION | Delivered | Closed |  | Saudi aramco supply |  |  |  | Yes | 90 | SAR |  |  | FOB | Port | Pending
229 | FAV | CC978 | User 37 | Civil | PR526582 | MAT72735 | 11-Mar-2026 | 18-Mar-2026 | CONTROL VALVE ACTUATOR REPAIR | On Hold | OPEN | 4514122577 | Al-Rushaid Trading Co. | 21-Mar-2026 | 12-Jul-2026 | 21-Mar-2026 |  | 30 | EUR | 209969.58 | 12240.82 | CIF | Warehouse | Done | 27-Jul-2026
230 | FAV | CC472 | User 38 | Civil | PR353500 | MAT29879 | 03/01/2026 | 15/01/2026 | PRESSURE TRANSMITTER HART PROTOCOL | Delivered | OPEN | 4514149527 | Saudi aramco supply | 10/02/2026 | 21/04/2026 |  | No | 90 | USD | 242720.02 | 18696.11 |  |  | Partial Delivery
231 | FAV | CC603 | User 49 | Civil | PR984569 | MAT73465 | 28-Jan-2026 | 09-Feb-2026 | PRESSURE TRANSMITTER HART PROTOCOL | RFQ | Open | 4514117510 | SABIC INDUSTRIAL | 24-Feb-2026 | 11-Apr-2026 | 24-Feb-2026 |  | 30 | USD | 232667.74 | 9460.17 | FOB | Warehouse | Delivered | 01-Apr-2026
232 | FAV | CC587 | User 10 |  | PR979747 | MAT57258 | 20-Jul-2026 | 06-Aug-2026 | PROCESS ISOLATION WINDOW SIGHT GLASS | PO | Closed | 4514163357 | GE Power Arabia | 17-Aug-2026 | 26-Nov-2026 | 17-Aug-2026 |  | 30 | USD | 36300.39 | 1737.86 | FOB | Site | In Transit
233 | HEV | CC738 | User 50 |  | PR426425 | MAT35146 | 2026/07/21 | 2026/07/31 | COOLING TOWER FILL MEDIA REPLACEMENT | PR |  | 4514134811 |  | 2026/08/30 | 2026/09/26 | 2026/08/30 | Yes | 45 | EUR | 77828.03 | 6059.71 | FOB | Port | In Transit
234 | FAV | CC257 | User 11 | INST | PR210790 | MAT60415 | 04/02/2026 | 14/02/2026 | COMPRESSOR OIL AND FILTER KIT | Cancelled | Open | 4514169093 | SABIC INDUSTRIAL | 20/02/2026 |  |  |  | 30 | EUR | 238817.26 | 13390.22 | CIF |  | Pending
235 | HEY | CC473 | User 30 | Civil | PR881509 | MAT21393 | 10-Nov-2025 |  | ELECTRICAL CABLE 3CX16MM ARMOURED | On Hold | Closed |  | Saudi Aramco Supply |  |  |  | No |  |  |  |  | CIF | Port | N/A
236 | HEY | CC527 | User 11 |  | PR387669 | MAT11091 | 04/23/2026 |  | CENTRIFUGAL PUMP MECHANICAL SEAL | RFQ | In Progress |  | Yokogawa ME |  |  |  |  | 30 | USD |  |  | FOB | Site | N/A
237 | HEY | CC301 | User 14 | Mechanical | PR580917 | MAT40520 | 23/06/2026 | 09/07/2026 | ELECTRICAL CABLE 3CX16MM ARMOURED | Cancelled | Open | 4514166629 | Emerson Process | 25/07/2026 | 14/11/2026 | 25/07/2026 | Yes | 90 |  | 24461.69 | 976.02 | FOB | Site | In Transit
238 |  | CC452 | User 4 | Instrumentation | PR159204 | MAT42131 | 15/07/2026 | 25/07/2026 | CONTROL VALVE ACTUATOR REPAIR |  | Closed | 4514195498 | Saudi aramco supply | 11/08/2026 | 09/12/2026 | 11/08/2026 | No | 60 | SAR | 239873.35 | 10852.44 | FOB | Port
239 | FAV | CC690 | User 50 | INST | PR329253 | MAT53103 | 07/26/2026 | 08/12/2026 | ELECTRICAL CABLE 3CX16MM ARMOURED |  | OPEN |  | Schneider Electric KSA |  |  |  | Yes | 30 | SAR |  |  |  | Site | N/A
240 |  | CC195 | User 35 | INST | PR990990 | MAT81824 | 03/05/2026 |  | SCAFFOLDING ERECTION AND DISMANTLING | PO | OPEN |  | Honeywell KSA |  |  |  | No | 60 | USD |  |  |  |  | N/A
241 | HEV | CC933 | User 9 | Process | PR387991 | MAT10289 | 06-May-2026 | 16-May-2026 | ANNUAL PM SERVICE FOR CHILLER UNIT | Cancelled | In Progress | 4514170466 |  | 28-May-2026 | 11-Jul-2026 | 28-May-2026 | YES |  | SAR | 216824.71 | 5037.79 | CIF | Warehouse | Partial Delivery
242 | HEY | CC194 | User 11 | Electrical | PR532641 | MAT29386 | 20-May-2026 |  | GATE VALVE 6 INCH CLASS 300 | On Hold | OPEN |  | Parker Hannifin |  |  |  |  | 45 | SAR |  |  |  | Site
243 | HEV | CC234 | User 7 | Civil | PR477270 | MAT18075 | 2025/11/09 | 2025/11/12 | PLC SPARE PARTS AND MODULES | RFQ | OPEN | 4514175657 |  | 2025/12/09 | 2026/02/21 | 2025/12/09 | YES | 45 | EUR | 200665.85 | 15239.88 |  | Site | Partial Delivery
244 | HEY | CC404 | User 30 | INST | PR338977 | MAT55896 | 2026-07-10 | 2026-07-17 | FLOWMETER CALIBRATION AND CERTIFICATION |  | In Progress | 4514129734 | Honeywell KSA | 2026-08-02 | 2026-11-06 | 2026-08-02 | YES | 90 | EUR | 56191.71 | 1995.35 |  |  | pending
245 | HEV | CC415 | User 18 | Civil | PR371616 | MAT37689 | 2026-06-02 | 2026-06-19 | PAINTING AND INSULATION CLADDING |  | OPEN | 4514163360 | Saudi aramco supply | 2026-07-17 | 2026-07-31 | 2026-07-17 | YES | 30 | SAR | 16153.86 | 560.3 | CIF |  | Del | 2026-08-08
246 | HEY | CC380 | User 29 | Electrical | PR653938 | MAT83457 | 15/05/2026 |  | COMPRESSOR OIL AND FILTER KIT | PO | Closed | [5 empty] | YES | 60 | USD |  |  |  | Site | N/A
247 | HEV | CC133 | User 9 |  | PR358518 | MAT78122 | 2026-06-20 | 2026-06-23 | CENTRIFUGAL PUMP MECHANICAL SEAL | PR | Closed | 4514159059 | Schneider Electric KSA | 2026-07-01 | 2026-10-24 | 2026-07-01 | Yes | 45 | USD | 141558.85 | 5025.07 | CIF |  | In Transit
248 | HEY | CC307 | User 13 | INST | PR692318 | MAT96501 | 21-Jan-2026 | 27-Jan-2026 | CENTRIFUGAL PUMP MECHANICAL SEAL | PR | Open | 4514149130 | Al Mojil Group | 18-Feb-2026 | 24-May-2026 | 18-Feb-2026 |  | 60 | USD | 134397.35 | 5498.42 | DAP | Site | Delivered | 04-Jun-2026
249 |  | CC486 | User 12 | Instrumentation | PR291953 | MAT28874 | 18-Jan-2026 | 22-Jan-2026 | FLOWMETER CALIBRATION AND CERTIFICATION | Delivered | Open |  | UNKNOWN VENDOR |  |  |  | Yes | 30 |  |  |  |  | Port | N/A
250 | FAV | CC731 | User 9 | Utilities | PR849034 | MAT68901 | 2026/06/07 | 2026/06/10 | PROCESS ISOLATION WINDOW SIGHT GLASS | On Hold | In Progress | 4514181762 | GE Power Arabia | 2026/07/07 | 2026/08/18 | 2026/07/07 |  |  | EUR | 718.81 | 29 | DAP | Site | Done | 2026/08/26
251 | HEY | CC123 | User 25 | Electrical | PR452779 | MAT79332 | 2026-01-05 | 2026-01-12 | UPS BATTERY REPLACEMENT 110V | Cancelled | Open | 4514144112 | SKF Arabia | 2026-01-19 | 2026-05-14 |  | YES | 30 | USD | 218306.81 | 6491.22 |  | Warehouse | pending
252 |  | CC436 | User 19 | Electrical | PR685850 | MAT62510 | 2025/11/13 |  | HEAT EXCHANGER CLEANING SERVICE | PR | Open |  | Siemens Arabia |  |  |  |  | 30 | USD |  |  | CIF | Port
253 | HEY | CC487 | User 16 | MECH | PR760673 | MAT13686 | 2026/05/30 | 2026/06/19 | PROCESS ISOLATION WINDOW SIGHT GLASS | Delivered |  |  | SABIC Industrial |  |  |  |  | 60 | SAR |  |  | FOB | Warehouse | N/A
254 | FAV | CC514 | User 9 | Civil | PR450580 | MAT96624 | 02-Nov-2025 | 16-Nov-2025 | CENTRIFUGAL PUMP MECHANICAL SEAL | Cancelled | In Progress | 4514126481 | UNKNOWN VENDOR | 07-Dec-2025 | 04-Jan-2026 | 07-Dec-2025 |  |  |  | 5357.74 | 266.99 |  |  | Pending
255 | HEY | CC258 | User 39 | INST | PR740419 | MAT37499 | 05/26/2026 |  | CENTRIFUGAL PUMP MECHANICAL SEAL | On Hold | Open |  | Schneider Electric KSA |  |  |  | No |  | USD |  |  | FOB | Site
256 | FAV | CC437 | User 18 | Instrumentation | PR723623 | MAT59698 | 2026-03-31 |  | COOLING TOWER FILL MEDIA REPLACEMENT |  | Open |  | Endress+Hauser |  |  |  |  | 30 | SAR |  |  | DAP
257 | HEY | CC265 | User 14 | Utilities | PR863929 | MAT28094 | 2026/04/22 |  | LABORATORY CHEMICALS AND REAGENTS | Delivered | Open |  | Al Mojil Group |  |  |  | No | 90 | USD |  |  |  | Warehouse | N/A
258 | FAV | CC429 | User 15 | Civil | PR981150 | MAT21956 | 02-Feb-2026 |  | FIRE DETECTION SYSTEM MAINTENANCE | On Hold | Open |  | SABIC Industrial |  |  |  |  | 30 | USD |  |  |  | Port | N/A
259 | FAV | CC273 | User 7 | Instrumentation | PR730207 | MAT95476 | 03/20/2026 | 03/31/2026 | PAINTING AND INSULATION CLADDING | PR | In Progress | 4514161702 | SABIC INDUSTRIAL | 04/20/2026 | 05/28/2026 | 04/20/2026 |  | 90 | USD | 122647.11 | 8867.66 |  | Site
260 | HEY | CC475 | User 10 | Utilities | PR829770 | MAT14405 | 14/06/2026 |  | PAINTING AND INSULATION CLADDING | On Hold | Open |  | UNKNOWN VENDOR |  |  |  | Yes | 90 |  |  |  |  | Warehouse
261 | HEY | CC262 | User 24 | Civil | PR398812 | MAT58876 | 13/06/2026 | 19/06/2026 | COMPRESSOR OIL AND FILTER KIT | Cancelled | In Progress |  | Al-Rushaid Trading Co. |  |  |  |  | 45 | SAR |  |  | FOB | Site | Pending
262 | FAV | CC798 | User 21 | MECH | PR902623 | MAT42604 | 11-Aug-2026 |  | COOLING TOWER FILL MEDIA REPLACEMENT | Cancelled |  |  | Siemens Arabia |  |  |  | No | 90 | SAR |  |  | CIF | Port
263 | FAV | CC493 | User 30 | Electrical | PR220603 | MAT72760 | 2026-07-26 | 2026-07-31 | PLC SPARE PARTS AND MODULES | On Hold | In Progress | 4514151157 | Schneider Electric KSA | 2026-08-09 | 2026-10-25 | 2026-08-09 | No | 90 | USD | 129121.75 | 9929.07 | CIF |  | Pending
264 | FAV | CC603 | User 47 | Utilities | PR984499 | MAT60354 | 2025/11/16 | 2025/11/19 | PROCESS ISOLATION WINDOW SIGHT GLASS | RFQ | Open | 4514143520 | Siemens Arabia | 2025/11/22 | 2026/03/22 | 2025/11/22 | YES | 60 | USD | 42178.8 | 3366.24 | FOB | Warehouse | Partial Delivery
265 | FAV | CC566 | User 33 | Electrical | PR591133 | MAT64450 | 2026-07-11 | 2026-07-21 | UPS BATTERY REPLACEMENT 110V | PR |  |  | SKF Arabia |  |  |  | YES | 60
266 | HEY | CC853 | User 3 |  | PR402433 | MAT83844 | 21/06/2026 | 09/07/2026 | PAINTING AND INSULATION CLADDING | PR | Closed | 4514151625 | SABIC Industrial | 23/07/2026 | 11/09/2026 | 23/07/2026 | Yes | 30 |  | 105823.88 | 7002.76 | DAP |  | Pending
267 | FAV | CC385 | User 12 | Instrumentation | PR229562 | MAT28604 | 07/02/2026 |  | HAWKER WET CELL BATTERY SET 24V | PR | In Progress |  | ABB Saudi Arabia |  |  |  | YES |  |  |  |  | CIF | Site
268 | FAV | CC147 | User 13 | Instrumentation | PR966109 | MAT86711 | 11/11/2025 | 26/11/2025 | COOLING TOWER FILL MEDIA REPLACEMENT | PO | OPEN | 4514114784 | Al Mojil Group | 21/12/2025 | 18/04/2026 |  | Yes | 45 | USD |  |  | FOB | Site | Delivered | 12/04/2026
269 | HEY | CC482 | User 10 | Civil | PR430731 | MAT55618 | 2026/02/24 |  | ELECTRICAL CABLE 3CX16MM ARMOURED | Cancelled | Closed |  | Al-Rushaid Trading Co. |  |  |  |  | 45 |  |  |  | CIF | Site
270 | HEY | CC165 | User 22 | Civil | PR485204 | MAT46500 | 12/06/2025 | 12/10/2025 | GATE VALVE 6 INCH CLASS 300 |  |  | 4514140733 | Saudi aramco supply | 12/24/2025 | 04/18/2026 | 12/24/2025 |  |  | EUR | 214427.66 | 6675.63 | CIF |  | Pending
271 | HEV | CC582 | User 42 | Utilities | PR680365 | MAT26993 | 2025-11-11 | 2025-11-13 | SCAFFOLDING ERECTION AND DISMANTLING |  | Open | 4514144289 | Emerson Process | 2025-12-07 | 2026-03-21 | 2025-12-07 |  | 45 | SAR | 227294.65 | 4604.14 |  | Site | Del | 2026-04-03
272 | HEY | CC682 | User 43 | Electrical | PR438495 | MAT26866 | 2026/08/09 | 2026/08/29 | LABORATORY CHEMICALS AND REAGENTS | RFQ | In Progress | 4514140851 | Parker Hannifin | 2026/09/12 | 2026/11/24 | 2026/09/12 |  | 30 | EUR | 61596.77 | 3206.24 |  | Port
273 |  | CC901 | User 38 | Utilities | PR449201 | MAT86812 | 2026-06-09 | 2026-06-24 | GATE VALVE 6 INCH CLASS 300 | On Hold | OPEN | 4514145682 | Saudi Aramco Supply | 2026-07-19 | 2026-09-02 | 2026-07-19 | No |  | USD | 109527.28 | 8211.42 |  | Warehouse
274 | FAV | CC929 | User 32 | Civil | PR729358 | MAT74258 | 19/11/2025 | 08/12/2025 | UPS BATTERY REPLACEMENT 110V | Delivered | Open | 4514185593 | SKF Arabia | 30/12/2025 | 18/04/2026 |  |  | 45 | SAR | 112695.07 | 6174.05 | FOB | Warehouse | DELIVERED | 29/04/2026
275 | HEY | CC473 | User 12 | Civil | PR248510 | MAT93159 | 2026-07-26 | 2026-08-10 | COMPRESSOR OIL AND FILTER KIT | PR | In Progress | 4514111088 | Emerson Process | 2026-08-18 | 2026-09-03 | 2026-08-18 | YES | 60 |  |  |  |  | Warehouse | Pending
276 | HEY | CC752 | User 15 | Electrical | PR289291 | MAT47914 | 13-Mar-2026 | 21-Mar-2026 | LABORATORY CHEMICALS AND REAGENTS | RFQ | In Progress | 4514140106 | ABB Saudi Arabia | 12-Apr-2026 |  | 12-Apr-2026 | No | 90 | USD | 169041.46 | 12046.77 | CIF | Port | N/A
277 | HEY | CC446 | User 16 | Instrumentation | PR749524 | MAT56379 | 2025-12-14 | 2026-01-02 | SAFETY VALVE TESTING AND CALIBRATION | On Hold | In Progress | 4514112099 | Saudi aramco supply | 2026-01-13 | 2026-02-28 | 2026-01-13 | No | 60 | USD |  |  | DAP |  | Done | 2026-03-14
278 | HEY | CC245 | User 6 | Instrumentation | PR636668 | MAT66275 | 2026-07-26 | 2026-07-28 | SAFETY VALVE TESTING AND CALIBRATION | RFQ | OPEN | 4514153117 | SABIC Industrial | 2026-08-02 | 2026-09-16 |  |  | 60 | SAR | 219839.74 | 9253.75 | FOB | Warehouse
279 | HEY | CC551 | User 38 |  | PR935502 | MAT56362 | 01/06/2026 |  | GATE VALVE 6 INCH CLASS 300 | Cancelled | Closed |  | Al Mojil Group | [5 empty] | EUR |  |  | DAP | Warehouse
280 | FAV | CC526 | User 6 | INST | PR175635 | MAT29165 | 06/02/2026 | 19/02/2026 | LABORATORY CHEMICALS AND REAGENTS | Delivered | Open | 4514160682 | Honeywell KSA | 17/03/2026 | 08/05/2026 | 17/03/2026 | No |  | USD | 125297.66 | 6095.43 | CIF | Warehouse | In Transit
281 | HEY | CC942 | User 41 | INST | PR124824 | MAT45289 | 18/02/2026 |  | HEAT EXCHANGER CLEANING SERVICE | RFQ | In Progress |  | Saudi aramco supply |  |  |  | YES |  | EUR |  |  | DAP
282 | HEY | CC958 | User 17 | Civil | PR464445 | MAT36274 | 03/15/2026 |  | PROCESS ISOLATION WINDOW SIGHT GLASS | RFQ | Open |  | Al Mojil Group |  |  |  |  | 45 | EUR |  |  | CIF | Site
283 | HEY | CC910 | User 19 |  | PR208884 | MAT17649 | 03/06/2026 | 03/11/2026 | HAWKER WET CELL BATTERY SET 24V | Cancelled | Open |  | SKF Arabia |  |  |  |  | 60 | SAR
284 |  | CC333 | User 8 | Process | PR363439 | MAT63048 | 15-Dec-2025 |  | ELECTRICAL CABLE 3CX16MM ARMOURED |  | Closed |  | Schneider Electric KSA |  |  |  |  | 60 |  |  |  | FOB
285 | HEY | CC828 | User 24 | Utilities | PR645640 | MAT48984 | 2025-12-31 |  | FIRE DETECTION SYSTEM MAINTENANCE | On Hold | In Progress |  | ABB Saudi Arabia |  |  |  |  | 30 |  |  |  |  | Warehouse | Pending
286 | FAV | CC551 | User 21 | Electrical | PR809388 | MAT76719 | 2026/01/11 |  | LEVEL TRANSMITTER INSTALLATION | RFQ | Closed |  | Endress+Hauser |  |  |  | No |  | EUR |  |  | DAP | Warehouse | N/A
287 | HEY | CC666 | User 29 | Electrical | PR434310 | MAT74335 | 05/03/2026 | 09/03/2026 | GATE VALVE 6 INCH CLASS 300 | RFQ | Closed | 4514196099 | Al-Rushaid Trading Co. | 27/03/2026 | 14/05/2026 | 27/03/2026 |  | 90 | USD |  |  | CIF |  | Partial Delivery
288 | HEV | CC264 | User 22 | INST | PR911033 | MAT15172 | 07/09/2026 |  | LEVEL TRANSMITTER INSTALLATION | PO | Open |  | Schneider Electric KSA |  |  |  |  | 45 |  |  |  | DAP | Port
289 | HEY | CC411 | User 23 | Civil | PR810892 | MAT29281 | 2026-06-13 | 2026-06-29 | PLC SPARE PARTS AND MODULES | On Hold | In Progress | 4514134650 | Parker Hannifin | 2026-07-17 | 2026-11-09 | 2026-07-17 | Yes | 45 | SAR | 169136.74 | 6791.53 | DAP | Site
290 | HEY | CC994 | User 15 | Process | PR256269 | MAT16251 | 01/04/2026 | 01/11/2026 | PLC SPARE PARTS AND MODULES |  | OPEN | 4514144170 | SABIC INDUSTRIAL | 01/27/2026 | 02/27/2026 |  | YES |  |  | 159648.71 | 11185.87 | DAP | Site
291 | HEV | CC693 | User 50 | Mechanical | PR673446 | MAT40954 | 2025/12/22 | 2026/01/04 | UPS BATTERY REPLACEMENT 110V | On Hold |  | 4514134881 | ABB Saudi Arabia | 2026/01/09 |  | 2026/01/09 |  | 60 | USD | 76906.57 | 3164.17 |  |  | Pending
292 | HEY | CC306 | User 17 |  | PR634058 | MAT66264 | 16/02/2026 |  | CONTROL VALVE ACTUATOR REPAIR | On Hold | In Progress |  | Parker Hannifin |  |  |  | No | 30 | USD |  |  | FOB | Site | Pending
293 | HEY | CC686 | User 24 | Mechanical | PR177003 | MAT42667 | 2026/05/14 |  | FLOWMETER CALIBRATION AND CERTIFICATION |  |  |  | Saudi Aramco Supply |  |  |  | YES | 45 | USD |  |  | CIF |  | Pending
294 | HEY | CC290 | User 3 | Process | PR864126 | MAT94459 | 15-Feb-2026 | 04-Mar-2026 | ELECTRICAL CABLE 3CX16MM ARMOURED | PR | OPEN | 4514126001 | GE Power Arabia | 26-Mar-2026 | 20-Jun-2026 | 26-Mar-2026 | No |  | EUR | 73449.56 | 2868.93 | FOB |  | delivered | 05-Jul-2026
295 | HEY | CC373 | User 8 | Civil | PR906071 | MAT94680 | 17/11/2025 | 01/12/2025 | HAWKER WET CELL BATTERY SET 24V | On Hold | In Progress | 4514199275 |  | 13/12/2025 | 18/01/2026 |  |  | 90 | USD | 32106.78 | 2001.34 | FOB
296 | HEY | CC948 | User 8 | Mechanical | PR596073 | MAT78129 | 03/26/2026 | 04/03/2026 | HAWKER WET CELL BATTERY SET 24V | RFQ |  | 4514144691 | Yokogawa ME | 04/15/2026 |  |  | Yes | 30 | SAR | 37638.82 | 2470.43 | CIF
297 | HEY | CC188 | User 19 | Process | PR358860 | MAT23439 | 07/13/2026 |  | PRESSURE TRANSMITTER HART PROTOCOL | Delivered | Closed |  | ABB Saudi Arabia |  |  |  | Yes | 60 | EUR |  |  | CIF | Site | Pending
298 | HEY | CC446 | User 45 | MECH | PR181769 | MAT98479 | 08/09/2026 | 08/25/2026 | FIRE DETECTION SYSTEM MAINTENANCE | RFQ | Open | 4514169524 | Siemens Arabia | 08/31/2026 | 10/10/2026 |  | No | 45 | USD | 156310 | 12408.73 | DAP | Warehouse | In Transit
299 | FAV | CC297 | User 48 | INST | PR424184 | MAT57050 | 27/06/2026 |  | GATE VALVE 6 INCH CLASS 300 | PO | Open |  | SABIC INDUSTRIAL |  |  |  | Yes | 30 | USD
300 | FAV | CC691 | User 45 | Electrical | PR765666 | MAT92413 | 17-Dec-2025 |  | UPS BATTERY REPLACEMENT 110V | Cancelled | OPEN |  | Parker Hannifin |  |  |  | YES | 45 | EUR |  |  | DAP | Warehouse | N/A